## Bug Metrics
IS203 G1-T3 Bug Metrics | [6 empty] | Points Calculation: Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
Iteration | Number of Bugs | Number of Low Impact | Number of High Impact | Number of Critical Impact | Bug Metrics Points | Action Done
2 | 0 | 0 | 0 | 0 | 0 | Insert debugging sessions to resolve the bugs
3 | 1 | 0 | 1 | 0 | 5 | Insert debugging session after deployment to resolve the bugs
4 | 0 | 0 | 0 | 0 | 0 | Insert debugging session after deployment to resolve the bugs
5 | 0 | 0 | 0 | 0 | 0 | An emergency debugging session was added to update the code according to the change in wiki requirements before UAT. Debugging sessions were added to resolve bugs identified after manual and automated UAT.
6 | 0 | 0 | 0 | 0 | 0 | Bugs were identified during UAT and resolved in debugging sessions before the final deployment.
Total | 1 | 0 | 1 | 0 | 5

## Bug Log
Iteration | Task S/N | Description | Where did it occur | How to reproduce | Who found it | Date Found | Date Solved | Time Taken (hr) | Severity (Impact) | Points Allocation | Point Accumulated Per Iteration | Status | Action | Pair Programmers
2 | 2-7.4 | Error - SQL exception | LoginDAO | When logging in from login.jsp | Mx | 2017-09-26 | 2017-09-26 | 0.1 | Critical | 10 | 10 | Fixed | Fix query statement in loginDAO | Joel MX
3 | 3-5 | Able to access home.jsp without logging in | Home.jsp | Without including protect.jsp in home.jsp page | Joel | 2017-09-27 | 2017-09-28 | 0.2 | High | 5 | 5 | Fixed | Added a protect.jsp page and include in the home.jsp and admin.jsp | Joel Joleen
3 | 3-5 | When accessing the home page again in from another tab, gets an error | Login/LoginServlet | When setting request attribute instead of session | Joel | 2017-09-28 | 2017-09-28 | 0.15 | High | 5 | 10 | Fixed | Change request.setAttribute to session.setAttribute | Joel Joleen
3 | 3-6 | Error - No Error Messages after bootstrap | Admin.jsp | Upload this-testcase.zip | Joel | 2017-09-29 |  | 0.3 | Low | 1 | 11 | Fixed | Added error msgs list in Admin.jsp | Joel Joleen
3 | 3-6 | java.sql.time -> when intializing Time object, the hours and minutes of the object do not correspond to the milliseconds that have been passed to the constructor | BasicLocationReportsServlet.java | Try to create a Time object (without using the deprecated method) | Shreyas | 2017-10-01 |  |  | High | 5 | 16 | Not Fixed |  | Shreyas, MX
3 | 3-8 | Error -Database not found error | DBConnection | Uploading data-se-4.zip and database software engineering not found | Joleen | 2017-10-02 | 2017-10-02 | 0.4 | Critical | 10 | 26 | Fixed | Create schema on PHPMYADMIN | Joel Joleen
3 | 3-8 | Error -Data Truncation too long for column | DBConnection | Uploading data-se-4.zip and varchar column 'semanticplace' for 25 | Joleen | 2017-10-03 | 2017-10-03 | 0.2 | Critical | 10 | 36 | Fixed | Change the length of varchar in 'semanticplace' column | Joel Joleen
3 | 3-8 | Error Msg appears in Admin.jsp after second test upload (File with no error) | Admin.jsp | Upload one file, then another one | Joel | 2017-10-03 |  |  | High | 5 | 41 | Not Fixed