## Slide 1: Project Management Review
Done by: G1T3

## Slide 2: Joleen
Team NO S.I.S.
Amanda
Shreyas
Ming Xuan
Joel

## Slide 3: Content page
Functionalities
Schedule
Metrics (schedule & bug)
Roles & responsibilities - Pair programming/rotation plan

## Slide 4: 1.Functionalities

## Slide 5: Functionalities
Login
Bootstrap
Heatmap
Basic Location Report
Automatic Group Identification
Dual Interfaces (UI and Web Services)
Our group does not intend to drop any functionalities.

## Slide 6: Do you plan to use any frameworks, or stick with MVC or JSP Model 1 or JSP only?
Chosen model: MVC
Benefits:
Individual pages would face less complexity
Lesser interaction between the UI and Java
Easier separation of roles for pair programming

## Slide 7: 2. Schedule

## Slide 8
Iteration No | Week | Period | Start Date | End Date | Milestones
Iteration 1 | Week 2 Week 3 | 14 days | 29/08/2017 | 12/09/2017 | Planning Design Diagrams Design Metric
Iteration 2 | Week 4 Week 5 | 14 days | 13/09/2017 | 26/09/2017 | Login Authentication Bootstrap
Iteration 3 | Week 6 Week 7 | 14 days | 27/09/2017 | 10/10/2017 | Supervisor Meeting 1 Primary Functions Top k popular places report Student breakdown report Web UI PM Review AWS Deployment
Iteration 4 | Week 8 Week 9 | 14 days | 11/10/2017 | 24/10/2017 | Primary Functions Heat Map Automated Group Identification
Iteration 5 | Week 10 Week 11 | 14 days | 25/10/2017 | 07/11/2017 | Supervisor Meeting 2 Primary Functions Top k people report Top k next places Dual Interfaces Application Demo
Iteration 6 | Week 12 Week 13 | 14 days | 08/11/2017 | 21/11/2017 | UAT Submission
Iteration 7 | Week 14 | 1 day | 22/11/2017 | 22/11/2017 | Presentation

## Slide 9: Broad Iteration
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Planning
Login
Bootstrap Function
S.B. Report
Top K Popular Place report
Heat Map
A.G.I
Top K people report
Top K next place report
UAT
Submission
Final Presentation

## Slide 10: Iteration 1 Critical Path: 6 Days, Slack: 9 days
Design
Planning
Discussion on Project Requirements and team's project iterative approach
(1 day)
Plan project broad schedule (1 day)
Create use case diagram (1 day)
Functionalities breakdown and logic sketching
(1 day)
Create Login sequence diagrams (1 day)
Prepare metrics (2 days)
Test Plan Preparation (1 day)
Create iteration breakdown (1 day)
Create database ER diagrams (1 day)
Create class diagram (1 day)

## Slide 11: Task Metric Result for Iteration 1
No. of Planned Tasks | Total no. of Tasks | Completed Tasks | Uncompleted Tasks
10 | 12 | 12 | 0
Result: 1.2 |  |  | 

## Slide 12: Iteration 2 Critical Path: 11 Days, Slack: 3 Day
Design
Testing
Planning
Create test cases (1 days)
Overall functions testing (1 day)
Create AGI sequence diagrams (1 day)
Create TOP K reports sequence diagrams (1 day)
Create Student Breakdown report sequence diagrams (1 day)
Create Bootstrap sequence diagrams (1 day)
Coding
Login Authentication (1 day)
Login Page (1 day)
DBConnection (1 day)
Upload Page (1 day)
Home Page (1 day)
Validation Location (1 day)
Validation Demographic ( 1 day)
Validation Location look up (1 day)
Debug Login (1 day)
Debug Bootstrap (1 day)
Upload Servlet (1 day)
Create HM sequence diagrams (1 day)

## Slide 13: Task Metric Result for Iteration 2
No. of Planned Tasks | Total no. of Tasks | Completed Tasks | Uncompleted Tasks
18 | 20 | 15 | 5
Result: 0.83 |  |  | 

## Slide 14: Iteration 3 Critical Path: 10 Days, Slack: 4 days
Coding
Testing
Planning
Integration
Deployment
Update test plan (1 day)
Create test cases (1 day)
Overall functions testing & debugging(1 day)
Create Top K DAO -
Top K places
(1 day)
Integrate required functions with previous functions (1 day)
Deployment on AWS (1 day)
PM Review Preparation (1 day)
PM Review (1 day)
UI Design (1 day)
Supervisor Meeting 1 (1 day)
Basic Location Report(Request, Servlet, Location DAO)
(1day)
Student breakdown request(Student, gender)(1day)
Student breakdown request(Schools)(1day)
Advanced breakdown 2 requests (1
day)
Advanced breakdown 3 requests (1
day)
Student breakdown request debugging (1 day)
Top K place request debugging (1 day)

## Slide 15: Updated Iteration 3 Critical Path: 9 Days, Slack: 5 days
Testing
Planning
Coding
Deployment
Overall functions testing & debugging (1 day)
Deployment on AWS (1 day)
PM Review Preparation; Creating Test cases, Update Test plan (1 day)
PM Review (1 day)
UI Design (1 day)
Supervisor Meeting 1 (1 day)
Validation location(1 day)
Validation demographics(1day)
Validation Location Lookup(1day)
Basic Location Report(Request, Servlet, Location DAO)
(1day)
Student breakdown request(Student, gender)(1day)
Student breakdown request(Schools)(1day)
Advanced breakdown 2 requests (1
day)
Advanced breakdown 3 requests (1
day)
Bootstrap debugging (1 day)
Student breakdown request debugging (1 day)
Integration
Integrate required functions with previous functions (1 day)
Develop JSON Authenticate
(1 days)

## Slide 16
Coding
Planning
Iteration 4 Critical Path: 11 Days, Slack: 3 days
Testing
Integration
Update test plan (1 day)
Create test cases (1 day)
Heat Map Request Page
(1 day)
Overall functions testing & debugging (1 day)
Heat Map Servlet
(2 days)
AGD request Page
(1 day)
Integrate search classes with previous functions (1 day)
Testing after redeployment (1 day)
Heat Map DAO
(1 days)
AGD Servlet
(1 day)
AGD DAO
(2 day)
AGD Interface
(1 day)
Deployment
Redeployment on AWS (1 day)
Heat Map Interface /UI
(1 days)
Heat Map Debugging
(1 days)
AGD Debugging
(1 days)
Develop JSON Student Breakdown report
(1 days)

## Slide 17
Testing
Coding
Planning
Integration
Deployment
Overall functions testing & debugging (1 day)
Update basic location report Servlet (1 day)
Integrate improved UI with previous functions (1 day)
Redeployment on AWS (1 day)
Supervisor meeting 2 (1 day)
Testing after redeployment (1 day)
Update test plan (1 day)
Create test cases (1 day)
Update Top K DAO-
Top K next place report
(1 day)
Update Top K DAO –
Top K people report
(1 day)
Iteration 5 Critical Path: 9 Days, Slack: 4 days
Demo of prototype and progress update (1 day)
UI – Improve Usability
(1 days)
Create Top K DAO -
Top K places
(1 day)
Develop JSON Heat Map
(1 days)
Develop JSON AGI
(1 days)
Top K reports debug
(1 days)
Develop JSON Top K
(1 days)
Redeployment on AWS for UAT(1 day)

## Slide 18
Design
Testing
Coding
Planning
Integration
Deployment
Overall functions testing & debugging (1 day)
Enhance UI (3 days)
Integrate improved UI with previous functions (1 day)
Final Deployment on AWS (1 day)
Post- UAT Improve application (3 days)
Manual UAT in class and automated UAT (1 day)
Testing after redeployment (1 day)
Final Presentation Slides (1 day)
Iteration 6 Critical Path: 8 Days, Buffer: 4 days

## Slide 19
Planning
Final presentation (1 day)
Final presentation rehearsal (1 day)
Iteration 7 Critical Path: 2 Days

## Slide 20: Burndown Report

## Slide 21: Roles and Responsibilities - PM Milestones
Supervisor Meeting 1 (02/10/2017) – Amanda
PM Review (04/10/2017) – Amanda
AWS Deployment (07/10/2017) – Amanda
Supervisor Meeting 2 (24/10/2017) - Joleen
Application Demo and Progress Update (25/10/2017) – Joleen
UAT (8/11/2017) – Shreyas
Final Submission (19/11/2017) – Shreyas
Final Presentation (22/11/2017) – Joel

## Slide 22: Task Distribution
Functions | Joel | Shreyas | Ming Xuan | Amanda | Joleen
Login Authentication |  |  |  |  | 
Bootstrap |  |  |  |  | 
Validations of csv files |  |  |  |  | 
Top K popular places report |  |  |  |  | 
Student breakdown report |  |  |  |  | 
Heat Map |  |  |  |  | 
Automated Group Identification |  |  |  |  | 
Dual Interface |  |  |  |  | 
Top k People report |  |  |  |  | 
Top k next places report |  |  |  |  | 
UI – Develop |  |  |  |  | 
UI – Improve Usability |  |  |  |  | 
UI – Enhance |  |  |  |  | 

## Slide 23: 3. Metrics

## Slide 24: Task Metrics
Severity | Action
TM < 50 | Immediately, inform your supervisor about the slip within 24 hours. Then use the same mitigation as the category 50 < TM < 90 and seriously consider dropping tasks.
50 < TM <= 90 | Re-estimate the tasks for the future iterations. Deduct the number of days behind schedule from slack/buffer days. If there is no more slack/buffer day, decide the functionalities to drop.
90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track. 1. Add/Deduct the number of days behind schedule from buffer days. 2. If there is no more buffer day, decide the functionalities to drop
110 < TM <= 150 | Gross over-estimated the effort required. 1. Re-estimate the tasks for the future iterations. 2. Add the number of days gained to buffer days.
150 < TM | 1. Immediately, inform your supervisor about the slip within 24 hours. 2. Then use the same mitigation as the category 110 < TM < 150

## Slide 25: Task Metrics
Chart: 
| 1 | 2 | 3
Y-Values | 1.25 | 0.86 | 0.5
Iteration
(2, 0.85)
(1, 1.2)
Iteration | Planned Tasks | Total Task | Task Completed | Task brought forward
1 | 10 | 12 | 12 | 0
2 | 18 | 20 | 15 | 5
3 | 22 | 23 | 8 ( as of now) | -
TM
Score
(2, 0.5)

## Slide 26: Task Metrics

## Slide 27: Mitigation plan for iteration 3
Iteration | Task | Problem | Mitigation Plan
3 | Validation Location.csv | We were not as confident when we just started our coding for this project  we therefore had to spend more time researching. At the same time, as we were rusty with our sequence diagrams more time was spent. | Move tasks to slack If necessary, push tasks to the next iteration.
 | Validation Demographics.csv |  | 
 | Validation Location Lookup.csv |  | 
 | Debug Bootstrap |  | 

## Slide 28: Bug Metrics
Iteration | No. of low impact bugs | No. of high impact bugs | No. of critical impact bugs | Total severity points | Bugs carried to next iteration
1 | 0 | 0 | 0 | 0 | 0
2 |  |  | 1 | 10 | 0
3 | 1 | 4 | 1 | 99 | - (still on going)

## Slide 29: 4. Roles & Responsibilities - Rotation Plan & Pair programming teams

## Slide 30: Different roles
Project Manager
Programmer
Notetaker
Time keeper

## Slide 31: Role: Project Manager
To help with:
  Activity planning for each iterations
  In charge of documentation
  To monitor progress of the group

## Slide 32: Role: Programmer
To help with:
  Coding different functionalities
  Testing, debugging
  Integration
  Deployment

## Slide 33: Role: Notetaker
To help with:
  Writing the minutes within 24 hours after meetings

## Slide 34: Role: Time-keeper
To help with:
  Ensuring that group is on task during meetings

## Slide 35: Rotation Plan
Iteration | Week duration | Project Manager | Pair Programming 1 | Pair Programming 2
1 | 2-3 | Joel | - | -
2 | 4-5 | Shreyas | Amanda, Joleen | Ming Xuan, Joel
3 | 6-7 | Amanda | Joel, Joleen | Ming Xuan, Shreyas
4 | 8-9 | Ming Xuan | Joel, Amanda | Shreyas, Joleen
5 | 10-11 | Joleen | Joel, Ming xuan | Shreyas, Amanda
6 | 12-13 | Shreyas | Amanda, Joel | Ming Xuan, Joleen
7 | 14 | Joel | Amanda, Joleen | Shreyas, Ming xuan

## Slide 36: Thank you!