## Bug Metrics
IS203 G1-T3 Bug Metrics | [6 empty] | Points Calculation: Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
Iteration | Number of Bugs | Number of Low Impact | Number of High Impact | Number of Critical Impact | Bug Metrics Points | Action Done
2 | 1 | 0 | 0 | 1 | 10 | Insert debugging sessions to resolve the bugs
3 | 7 | 1 | 4 | 2 | 41 | Insert debugging session after deployment to resolve the bugs
4 | 10 | 0 | 7 | 3 | 65 | Insert debugging session after deployment to resolve the bugs
5 | 39 | 0 | 38 | 1 | 205 | An emergency debugging session was added to update the code according to the change in wiki requirements before UAT. Debugging sessions were added to resolve bugs identified after manual and automated UAT.
6 | 18 | 0 | 18 | 0 | 85 | Bugs were identified during UAT and resolved in debugging sessions before the final deployment.
Total | 75 | 1 | 67 | 7 | 406

## Bug Log
Iteration | Task S/N | Description | Where did it occur | How to reproduce | Who found it | Date Found | Date Solved | Time Taken (hr) | Severity (Impact) | Points Allocation | Point Accumulated Per Iteration | Status | Action | Pair Programmers
2 | 2-7.4 | Error - SQL exception | LoginDAO | When logging in from login.jsp | Mx | 2017-09-26 | 2017-09-26 | 0.1 | Critical | 10 | 10 | Fixed | Fix query statement in loginDAO | Joel MX
3 | 3-5 | Able to access home.jsp without logging in | Home.jsp | Without including protect.jsp in home.jsp page | Joel | 2017-09-27 | 2017-09-28 | 0.2 | High | 5 | 5 | Fixed | Added a protect.jsp page and include in the home.jsp and admin.jsp | Joel Joleen
3 | 3-5 | When accessing the home page again in from another tab, gets an error | Login/LoginServlet | When setting request attribute instead of session | Joel | 2017-09-28 | 2017-09-28 | 0.15 | High | 5 | 10 | Fixed | Change request.setAttribute to session.setAttribute | Joel Joleen
3 | 3-6 | Error - No Error Messages after bootstrap | Admin.jsp | Upload this-testcase.zip | Joel | 2017-09-29 | 2017-10-06 | 0.3 | Low | 1 | 11 | Fixed | Added error msgs list in Admin.jsp | Joel Joleen
3 | 3-6 | java.sql.time -> when intializing Time object, the hours and minutes of the object do not correspond to the milliseconds that have been passed to the constructor | BasicLocationReportsServlet.java | Try to create a Time object (without using the deprecated method) | Shreyas | 2017-10-01 | 2017-10-04 | 0.5 | High | 5 | 16 | Fixed | Take user input as a String and append 00 as milliseconds to create time to be used for determining the range of chosen time to be passed into the SQL statement | Shreyas, MX
3 | 3-8 | Error -Database not found error | DBConnection | Uploading data-se-4.zip and database software engineering not found | Joleen | 2017-10-02 | 2017-10-02 | 0.4 | Critical | 10 | 26 | Fixed | Create schema on PHPMYADMIN | Joel Joleen
3 | 3-8 | Error -Data Truncation too long for column | DBConnection | Uploading data-se-4.zip and varchar column 'semanticplace' for 25 | Joleen | 2017-10-03 | 2017-10-03 | 0.2 | Critical | 10 | 36 | Fixed | Change the length of varchar in 'semanticplace' column | Joel Joleen
3 | 3-14 | Error Msg appears in Admin.jsp after second test upload (File with no error) | Admin.jsp | Upload one file, then another one | Joel | 2017-10-06 | 2017-10-06 | 0.2 | High | 5 | 41 | Fixed | Add a .clear method for errorlist as well as to sort in request clsas instead of session | Joel Joleen
4 | 4-16.2 | Processed data output for breakdown by Year is incorrect | BreakdownReports.jsp | Fill option1 with year and generate report | Mx | 2017-10-11 | 2017-10-12 | 0.1 | Critical | 10 | 10 | Fixed | Removed an incorrect '!' that was causing logic error that was translated to display page | Shreyas, MX
4 | 4-3.4 | Heatmap script to colour map not working | HeatMaps.jsp | Try sending a request for heatmap (any floor) | JM | 2017-10-15 | 2017-10-16 | 1 | High | 5 | 15 | Fixed | Error was with JSON parsing. Used single quotes instead double quotes | JM, Shreyas
4 | 4-7 | For L2 and L3, the SRs (at the top) are not getting coloured | HeatMaps.jsp, L2.svg, L3.svg | Request Hetmap for L2 or L3 | Shreyas | 2017-10-16 | 2017-10-21 | 3 | High | 5 | 20 | Fixed | Replaced '.' with 'n' in semantic place string | JM, Shreyas
4 | 4-5.4 | Wrong year, year can be more than 4 digits | AutomaticGroupIdentificaiton.jsp | Type 123456 while inputting year | Amanda | 2017-10-18 | 2017-10-19 | 0.5 | High | 5 | 25 | Fixed | Add a maximum value for the html form | Amanda , Joel
4 | 4-5.4 | Future date | AutomaticGroupIdentificaiton.jsp | Type 2020 for year input | Amanda | 2017-10-18 | 2017-10-19 | 0.5 | High | 5 | 30 | Fixed | Add a if-condition to within agdDAO to fix the null pointer | Amanda , Joel
4 | 4-5.4 | Prehistoric date | AutomaticGroupIdentificaiton.jsp | Type 1234 for year input | Joel | 2017-10-18 | 2017-10-19 | 0.5 | High | 5 | 35 | Fixed | Add a if-condition to within agdDAO to fix the null pointer | Amanda , Joel
4 | 4-5.4 | Missing timing when submitting form | AutomaticGroupIdentificaiton.jsp | Submits a form with missing timing | Joel | 2017-10-18 | 2017-10-19 | 0.1 | High | 5 | 40 | Fixed | Add required to html form tags | Amanda , Joel
4 | 4-5.4 | Missing date when submitting form | AutomaticGroupIdentificaiton.jsp | Submits a form with missing date | Amanda | 2017-10-18 | 2017-10-19 | 0.1 | High | 5 | 45 | Fixed | Add required to html form tags | Amanda , Joel
4 | 4-14 | Upload without choosing a file | Admin.jsp | Upload without choosing a file | MingXuan | 2017-10-21 | 2017-10-21 | 0.5 | Critical | 10 | 55 | Fixed | Add required to html form tags | Amanda , Joel
4 | 4-14 | Error Message of previous upload is shown in second upload | Admin.jsp | Upload one file, then another one | Amanda | 2017-10-21 | 2017-10-21 | 0.5 | Critical | 10 | 65 | Fixed | Editted codes in Bootstrap.servlet | Amanda , Joel
5 | 5-12 | Incorrect Date input (String 10 characters or less ) blank json output comes out | JsonBreakdownReport.java | Enter date 1234567890 | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 5 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect Date input (String 11 characters or more), blank json output comes out | JsonBreakdownReport.java | Enter date as12345678901 | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 10 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect Date input, blank json output comes out | JsonBreakdownReport.java | Enter date as 2017-02-06 11:15:00 | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 15 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect Date input , extra integer in minutes | JsonBreakdownReport.java | Enter date as 2017-02-06T11:115:00 | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 20 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect Date input, extra integer In seconds | JsonBreakdownReport.java | Enter date as 2017-02-06T11:15:001 | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 25 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Missing date, blank json output outputs | JsonBreakdownReport.java | Enters correct token, order and have date missing | Joleen | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 30 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Blank date, blank json output outputs | JsonBreakdownReport.java | Enters correct token, order and have date blank | Joel | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 35 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect order. Correct date, correct token | JsonBreakdownReport.java | Enter incorrect order ",,,,,year" and correct date and token | Joel | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 40 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Incorrect order. Correct date, correct token | JsonBreakdownReport.java | Enter incorrect order "year,,,," and correct date and token | Joel | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 45 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | blank order. Correct date, correct token | JsonBreakdownReport.java | Enter correct date and token, order is blank | Joel | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 50 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | missing order. Correct date, correct token | JsonBreakdownReport.java | Enter correct date and token, order missing | Joel | 2017-11-03 | 2017-11-03 | 0.2 | High | 5 | 55 | Fixed | Edit code in Breakdownreport json | Ming Xuan, Amanda
5 | 5-12 | Wrong hour value passed but results come out as success | JsonAGD.java | Enter date as 2017-12-06T99:00:00 | Joel | 2017-11-03 | 2017-11-04 | 0.5 | High | 5 | 60 | Fixed | Edit code in TimeUtility | Ming Xuan, Amanda
5 | 5-12 | Wrong mins value passed but results come out as success | JsonAGD.java | Enter date as 2017-12-06T09:79:00 | Joel | 2017-11-03 | 2017-11-04 | 0.5 | High | 5 | 65 | Fixed | Edit code in TimeUtility | Ming Xuan, Amanda
5 | 5-12 | Wrong seconds value passed but results come out as success | JsonAGD.java | Enter date as 2017-12-06T10:15:005555 | Joel | 2017-11-03 | 2017-11-04 | 0.5 | High | 5 | 70 | Fixed | Edit code in TimeUtility | Ming Xuan, Amanda
5 | 5-12 | Wrong date passed but results come out as success | JsonAGD.java | Enter date as 2017-02-31T10:15:00 | MingXuan | 2017-11-03 | 2017-11-04 | 0.5 | High | 5 | 75 | Fixed | Edit code in TimeUtility | Ming Xuan, Amanda
5 | 5-12 | No common validation for username and password field | JsonLoginAuthentication.jsp | Remove common validation code | Amanda | 2017-11-03 | 2017-11-04 | 0.5 | Critical | 10 | 85 | Fixed | Added common validation code for username and password fields | Ming Xuan, Amanda
5 | 5-12 | When date is blank, error message is "invalid floor" | JsonHeatmap.java | Enter a blank date | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 90 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When date is missing error message is "invalid floor" | JsonHeatmap.java | Do not enter any date | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 95 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When incorrect date is entered error message is "invalid floor" | JsonHeatmap.java | Enter incorrect date, in to form of random string, or invalid format | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 100 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When incorrect date is entered ('T' is missing) no error message shown | JsonHeatmap.java | Enter incorrect date, where 'T' is missing (but there is a space in between day and time) | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 105 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When floor is blank, error message is "invalid floor" | JsonHeatmap.java | Enter a blank floor | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 110 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When floor is missing error message is "invalid floor" | JsonHeatmap.java | Do not enter any floor | Shreyas | 2017-11-03 | 2017-11-04 | 0.2 | High | 5 | 115 | Fixed | Editted JsonHeatmap to account for corner case | Ming Xuan, Amanda
5 | 5-12 | When correct token, origin, date and missing k, output is not according to rank | JsonTopKNextPlaces.java | Enter a correct date, origin, date and missing k | MingXuan | 2017-11-03 | 2017-11-05 | 0.4 | High | 5 | 120 | Fixed | Add Collections.sort in JsonTopKNextPlaces.java | Joel,Shreyas
5 | 5-12 | When correct token, origin, date and k , output is not according to rank | JsonTopKNextPlaces.java | Enter a correct date, origin, date and k | MingXuan | 2017-11-03 | 2017-11-05 | 0.4 | High | 5 | 125 | Fixed | Add Collections.sort in JsonTopKNextPlaces.java | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKNextPlaces.jsp | Enter a form without typing in date and time | MingXuan | 2017-11-03 | 2017-11-05 | 0.2 | High | 5 | 130 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKNextPlaces.jsp | Enter a form without typing in date | MingXuan | 2017-11-03 | 2017-11-05 | 0.2 | High | 5 | 135 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKNextPlaces.jsp | Enter a form without typing in time | MingXuan | 2017-11-03 | 2017-11-05 | 0.2 | High | 5 | 140 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-12 | After submitting form, co location time not shown for each companion | TopKCompanion.jsp | Enter Rank: 3, Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017, Time: 10:15 AM | MingXuan | 2017-11-03 | 2017-11-05 | 0.2 | High | 5 | 145 | Fixed | Edit TopKCompanion to show co-location time | Joel,Shreyas
5 | 5-12 | After submitting form, a table is shown when there are no companions | TopKCompanion.jsp | Enter Rank: 3, Student: 0012a371ef9b4472e1ab2397b0db730550c9ec87 Date: 06/02/2017, Time: 10:15 AM | MingXuan | 2017-11-03 | 2017-11-05 | 0.2 | High | 5 | 150 | Fixed | Edit TopKCompanion to account for corner case | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKPopularPlaces.jsp | Enter a form without typing in date and time | Joleen | 2017-11-03 | 2017-11-05 | 0.1 | High | 5 | 155 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKPopularPlaces.jsp | Enter a form without typing in date | Joleen | 2017-11-03 | 2017-11-05 | 0.1 | High | 5 | 160 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-12 | HTTPS: Status 500. Index out of bound for string exception | TopKPopularPlaces.jsp | Enter a form without typing in time | Joleen | 2017-11-03 | 2017-11-05 | 0.1 | High | 5 | 165 | Fixed | Editted HTML form code for required inputs | Joel,Shreyas
5 | 5-18 | Second bootstrap with an invalid file type comes out the previous bootstrap error messages | JsonBootstrap.java | Enter a second form for bootstrap | Amanda | 2017-11-05 | 2017-11-05 | 0.3 | High | 5 | 170 | Fixed | Edit JsonBootstrap.java to clear pre-existing datas | Amanda, Ming Xuan
5 | 5-18 | Second update with an invalid file type comes out the previous update error messages | JsonUpdate.java | Enter a second form for update | Amanda | 2017-11-05 | 2017-11-05 | 0.3 | High | 5 | 175 | Fixed | Edit JsonUpdate.java to clear pre-existing datas | Amanda, Ming Xuan
5 | 5-18 | Second bootstrap with an valid file type but invalid inner files comes out the previous bootstrap error messages | JsonBootstrap.java | Enter a second form for bootstrap with valid file type but invalid files | Amanda | 2017-11-05 | 2017-11-05 | 0.3 | High | 5 | 180 | Fixed | Edit JsonBootstrap.java to clear pre-existing datas | Amanda, Ming Xuan
5 | 5-18 | Second upload with an valid file type but invalid inner files comes out the previous upload error messages | JsonUpdate.java | Enter a second form for bootstrap with valid file type but invalid files | Amanda | 2017-11-05 | 2017-11-05 | 0.3 | High | 5 | 185 | Fixed | Edit JsonUpdate.java to clear pre-existing datas | Amanda, Ming Xuan
5 | 5-20 | JSON student breakdown report met with null pointer exception when there is a missing date input | AWS Testing: JsonBreakdownReport.java | Do not enter any date parameter for json request | MingXuan | 2017-11-05 | 2017-11-05 | 0.1 | High | 5 | 190 | Fixed | Edit JsonBreakdownRepot.java to account for missing date case | Amanda, Ming Xuan
5 | 5-20 | Breakdown Report for gender option M and F was in incorrect order | AWS Testing: BreakdownReport.jsp | Generate breakdown report with gender in option,but not last option | Joel | 2017-11-05 | 2017-11-05 | 0.2 | High | 5 | 195 | Fixed | Edited BasicLocationReports files to ensure that M and F sorting is done right | Amanda, Ming Xuan
5 | 5-20 | JSON student breakdown output number did not tally with output parameter | AWS Testing: JsonBreakdownReport.java | input 2 or more options parameters when generating JSON request | Joel | 2017-11-05 | 2017-11-05 | 0.2 | High | 5 | 200 | Fixed | Edit JsonBreakdownRepot.java to display required output | Amanda, Ming Xuan
6 | 6-1 | Bootstrap invalids valid emails for demographs.csv | DemographicsValidator.java | Upload uat-data1 file for bootstrap | Shreyas | 2017-11-08 | 2017-11-13 | 1 | High | 5 | 5 | Fixed | Edit Demographics Validator to include checks for Email to follow wikipedia's standard | Joel, Joleen
6 | 6-1 | Heatmap not showing crowd density due to svg location name not detected | B1.svg, L1.svg, L2.svg, L3.svg, L4.svg, L5.svg | Upload uat-data1 file for bootstrap, select Date/time: 2017-3-31 3:15pm, Level:L2 | Amanda | 2017-11-08 | 2017-11-17 | 0.5 | High | 5 | 5 | Fixed | Edit HeatMap codes and svg files to be locationid instead of semantic place location | Joel, Joleen
6 | 6-1 | Basic Location Report does not show statistics for one option | BreakdownReports.jsp | Upload uat-data1 file for bootstrap, selectDate/time:2017-3-31 4:15pm, Filtering condition:Year | Amanda | 2017-11-08 | 2017-01-10 | 1 | High | 5 | 10 | Fixed | Edit BreakdownReport.jsp to add code that show percentage for single option that was previously missing. | Amanda, Ming Xuan
6 | 6-1 | Top-K popular places does not show ties at K-rank | TopKPopularPlaces.jsp | Upload uat-data1 file for bootstrap, select Date/time: 2017-3-31 4:45pm, K:2 | Amanda | 2017-11-08 | 2017-11-15 | 0.2 | High | 5 | 15 | Fixed | Edit TopKPopularPlaces to address ties in k-ranks | Amanda, Ming Xuan
6 | 6-1 | Top-k Companion does not show companion when user does not belong in demographics.csv | TopKCompanion.jsp | Upload uat-data1 file for bootstrap, select Date/time: 2017-4-1 12:15pm, MAC address: a123456789012345678901234567890123456789, K:3 | MingXuan | 2017-11-08 | 2017-11-15 | 1.1 | High | 5 | 20 | Fixed | Edit LocationReportDAO to account for the function to include users that are not in demographics.csv | Joel, Joleen
6 | 6-1 | Top-K next places does not show correct values for people with location updates | TopKNextPlaces.jsp | Upload uat-data1 file for bootstrap, select Date/time: 2017-4-1 3:30pm, Origin place: SMUSISL2SR2.1(New), K: 3 | MingXuan | 2017-11-08 | 2017-11-15 | 1.2 | High | 5 | 25 | Fixed | Edit LocationReportDAO for TopKNextPlaces SQL logic check to account for correct movement tracking | Amanda, Ming Xuan
6 | 6-1 | Automatic group detection does not show the correct number of groups and location id | AutomaticGroupIdentificaiton.jsp | Upload uat-data1 file for bootstrap, select Date/time: 2017-10-27 12:15pm | Joleen | 2017-11-08 | 2017-11-15 | 2 | High | 5 | 30 | Fixed | Edit StudentDAO to account for intermediate intervals that are past 5 minutes for correct location timing intervals | Joel, Joleen
6 | 6-1 | Automatic group detection not accepting seconds input | AutomaticGroupIdentificaiton.jsp | Upload uat-data1 file for bootstrap, select Date/time: 2017-10-27 12:14:59pm | Joleen | 2017-11-08 | 2017-11-10 | 1 | High | 5 | 35 | Fixed | Made changes to TimeUtility.java to account for seconds and more accurate calculation for time window. | Amanda, Ming Xuan
6 | 6-1 | Update additional files, wrong validation for emails and location repeated rows. Invalid update | DemographicsValidator.java, LocationValidator.java | Upload uat-data1 file for bootstrap, then uat-data2.zip | Shreyas | 2017-11-08 | 2017-11-13 | 1 | High | 5 | 40 | Fixed | Edit LocationValidator to include more checks for invalid timestamps | Joel, Joleen
6 | 6-1 | Bootstrap validation - Validate that the system checks for invalid data entries | DemographicsValidator.java, LocationValidator.java, LoationLookupValidator.java | Upload uat-data3 file for bootstrap | Joel | 2017-11-08 | 2017-11-13 | 1 | High | 5 | 45 | Fixed | Edit LocationLookUp.validator for semantic-place validation based on wikipedia's standards, LocationValidator for duplicate row validation to include the correct row numbers | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json Login | JsonLoginAuthentication.java | Enter username=admin, password=I-Love-SE-Deep-Deep | Joel | 2017-11-14 | 2017-11-15 | 0.1 | High | 5 | 50 | Fixed | Edit JsonLoginAuthentic to include invalid username/password into a json array | Joel, Joleen
6 | 6-1 | Invalid Json Output for JsonHeatmap. Values are not sorted by semantic-place | JsonHeatmap.java | Enter valid token, floor=2, date=2017-03-31T15:15:00 | Joel | 2017-11-14 | 2017-11-15 | 0.2 | High | 5 | 55 | Fixed | Edit changes in JsonHeatmap, heatmap dao and heatmap servlet for hashmaps to treemaps for easy sorting | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json Basic Location Report where year values are in int not in string | JsonBreakdownReport.java | Enter valid token, order=year,date=2017-03-31T16:15:00 | Joel | 2017-11-14 | 2017-11-15 | 0.1 | High | 5 | 60 | Fixed | Add an if-statement in jsonBreakdownReport to cover for year cases for inner map, middle and other maps | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json Basic Location Report where multiple options are chosen but intermediate option counts are in string and not in int format | JsonBreakdownReport.java | Enter valid token, order=year,school,gender, date=2017-03-31T16:15:00 | Joel | 2017-11-14 | 2017-11-15 | 0.1 | High | 5 | 65 | Fixed | Edit jsonBreakdownReport to convert intermediate counts from string to int format | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json Popular Places where semantic place message is spelt wrongly | JsonTopKPopularPlaces.java | Enter valid token, k=2, date=2017-03-31T15:15:00 | Joel | 2017-11-14 | 2017-11-15 | 0.1 | High | 5 | 70 | Fixed | Edit JsonTopKPopularPlaces spelling for semantic place to correct spelling for jsonObject | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json Popular Places where ties not shown for k-rank | JsonTopKPopularPlaces.java | Enter valid token, k=2, date=2017-03-31T16:45:00 | Joel | 2017-11-14 | 2017-11-15 | 0.2 | High | 5 | 75 | Fixed | Edit JsonTopKPopularPlaces to account for ties in k-rank | Joel, Joleen
6 | 6-1 | Invalid Json Output for Json AGD where locationID should be in int not string format | JsonAGD.java | Enter valid token, date=2017-10-27T12:15:00 | Joel | 2017-11-14 | 2017-11-15 | 0.2 | High | 5 | 80 | Fixed | Edit JsonAGD to change locationids to string | Joel, Joleen
6 | 6-1 | Invalid Json Output for bootstrap where error message in files should be sorted in alphabetical order | JsonBootstrap.java | Enter valid token, bootstrap.zip | Joel | 2017-11-14 | 2017-11-15 | 0.2 | High | 5 | 85 | Fixed | Edit JsonBootstrap to show error messages in sorted file alphabetically | Joel, Joleen