## Slide 1: Application Demo and Progress Updates
Done by: G1T3

## Slide 2
Team NO S.I.S.
Amanda
Shreyas
Ming Xuan
Joel
Joleen

## Slide 3: Content page
Functionalities
Improvements made
Progress Updates and Schedule
Metrics
Roles & responsibilities
Notes: Spill-overs  mitigation

## Slide 4: 1.1 Application Functionalities
Login
Bootstrap
Heatmap
Basic Location Report
Automatic Group Detection
Dual Interfaces (UI and Web Services)
Our group does not intend to drop any functionalities.

## Slide 5: 1.2 Chosen Framework
Model View Controller
Benefits:
Individual pages would face less complexity
Lesser interaction between the UI and Java
Easier separation of roles for pair programming

## Slide 6: Improvements Made
From PM REVIEW

## Slide 7: 2.1 Updating Schedule
Issues | Improvements
Too much slack (5-6 days) between iterations causes each iteration to feel too rushed. | Improved time management by spreading range of tasks across the full time frame available for each iteration. (Not more than 3 days of slack)
Some tasks were over generalized. | Broke down general tasks into detailed sub-tasks to better account for project progress .
Lack of test planning especially after deployment. | Added testing phase after deployment to ensure that deployed application runs smoothly.

## Slide 8: 2.2 Updates on metrics
Issues | Improvements
Missing task metric documents in git repository | Added in missing task metric documents to ensure clarity in tracking of progress.

## Slide 9: Schedule
Broad iteration Updates

## Slide 10
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Planning
Login
Bootstrap Function
S.B. Report
Top K Popular Place report
Heat Map
A.G.I
Top K people report
Top K next place report
UAT
Submission
Final Presentation
3.1 Previous Iteration Overview
Notes: Old Iteration Overview

## Slide 11
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Planning
Login
Bootstrap
S.B. Report
Heat Map
A.G.I
UAT
Submission
Final Presentation
Top K Functions
Bootstrap
Validation
Advanced S.B. Report
Post UAT updates
3.2 New Iteration Overview
Notes: New updated iteration overview.

## Slide 12
3.3 Updates in New Iteration
Actions Taken | Reasons
Bootstrap functionality was stretched through 2 iterations. | Bootstrap validation task was a spillover from iteration 2 to 3.
Student Breakdown Report was spilt into basic and advanced functionality. | Advanced function was a spillover function from iteration 3 to 4.
Shifted all Top K functions into iteration 5. | Similar functionality easier to be done together.
Notes: Added slide to explain changes in iteration tasks

## Slide 13: Schedule
Updated Iteration Timeline

## Slide 14
Iteration No | Week | Period | Start Date | End Date | Milestones/Tasks Done
Iteration 1 | Week 2 Week 3 | 14 days | 29/08/2017 | 12/09/2017 | Determine Schedule Backbone Design Diagrams Setting Metrics
Iteration 2 | Week 4 Week 5 | 14 days | 13/09/2017 | 26/09/2017 | Design Diagrams Login Bootstrap
Iteration 3 | Week 6 Week 7 | 14 days | 27/09/2017 | 10/10/2017 | Bootstrap Validation Supervisor Meeting 1 Basic Student Breakdown Report Web UI JSON Authenticate PM Review AWS Deployment
Iteration 4 | Week 8 Week 9 | 14 days | 11/10/2017 | 24/10/2017 | Advanced Student Breakdown Report Heat Map Automated Group Identification (AGI) JSON Bootstrap AWS Deployment Preparation for Application Demo

## Slide 15
Iteration No | Week | Period | Start Date | End Date | Milestones/Tasks Done
Iteration 5 | Week 10 Week 11 | 14 days | 25/10/2017 | 07/11/2017 | Supervisor Meeting 2 Top k functions JSON Heat Map JSON AGI JSON Top k Functions AWS Deployment Application Demo
Iteration 6 | Week 12 Week 13 | 14 days | 08/11/2017 | 21/11/2017 | UAT Post UAT application improvements AWS Deployment Final Presentation Preparation Submission
Iteration 7 | Week 14 | 1 day | 22/11/2017 | 22/11/2017 | Presentation

## Slide 16: Schedule
Progress Updates

## Slide 17: 3.4 What have we done?
Current Iteration:
  Iteration 4 (End date 24th October)
Application Functions
  Login
  Bootstrap
  Student Breakdown Report
  Heat Map
  AGI
  JSON Authenticate
  JSON Bootstrap
Uncompleted Application Functions
  Top K functions
  JSON for other Features

## Slide 18: 3.4 What have we done?
Milestones completed
  PM Review
  Supervisor Meeting 1
  Preparation of App Demo
Milestones left
  App Demo
  Supervisor Meeting 2
  Preparation for UAT
  UAT
  App Submission
  Preparation for Final Presentation
  Final Presentation

## Slide 19: 3.5 Challenges Faced – Spill over
Tasks Spilled Over | Problem | Action Taken
Advanced breakdown 2 requests | Had issues with functionality of Student Breakdown Report - storing of intermediate values of raw count values and percentage values when user selected two or three options for breakdown report. Printing of the results on the view page appropriately based on the user’s choice of option. | We planned for the tasks to be completed in the early half of iteration 4. The programming pair for the spillover task was in charge of completing the spillover task.
Advanced breakdown 2 requests and Chart for one request |  | 
Advanced breakdown 3 requests and output for two and three requests |  | 
Testing of Advanced Breakdown request |  | 
Debugging of Advanced Breakdown |  | 

## Slide 20: Schedule
Critical path

## Slide 21
Planning
Coding
Deployment
Overall functions testing & debugging (1 day)
Deployment on AWS and debug (1 day)
PM Review Preparation; Creating Test cases, Update Test plan (1 day)
PM Review (1 day)
UI Design (1 day)
Supervisor Meeting 1 (1 day)
Validation location(1 day)
Validation demographics(1day)
Validation Location Lookup(1day)
Basic Location Report, Location DAO)
(1day)
Student breakdown one request(2 day)
Advanced Student breakdown two request(1day)
Advanced student breakdown 3 requests (1
day)
Advanced breakdown 3 requests (1
day)
Bootstrap debugging (2 day)
Student breakdown request debugging (1 day)
Integration
Integrate required functions with previous functions (2 day)
Develop JSON Authenticate
(1 days)
Testing
Iteration 3 Critical Path: 12 days , Slack: 2 days

## Slide 22
Coding
Planning
Iteration 4 Critical Path: 14 days
Testing
Integration
Update test plan (1 day)
Create test cases (1 day)
Heat Map Request Page
(1 day)
Overall functions testing & debugging (1 day)
Heat Map Servlet
(1 days)
AGD request Page
(1 day)
Integrate search classes with previous functions (1 day)
Testing after deployment (1 day)
Heat Map DAO
(2 days)
AGD Servlet
(1 day)
AGD DAO
(2 day)
AGD Interface
(1 day)
Deployment
Deployment on AWS
(1 day)
Heat Map Interface /UI
(1 days)
Heat Map Debugging
(1 days)
AGD Debugging
(1 days)
Develop JSON Student Breakdown report
(1 days)
Debugging after AWS testing(1 day)
Redeployment on AWS (1 day)

## Slide 23
Testing
Coding
Planning
Integration
Deployment
Overall functions testing & debugging (1 day)
Update basic location report Servlet (1 day)
Integrate improved UI with previous functions (1 day)
Deployment on AWS and testing (1 day)
Supervisor meeting 2
(0.5 day)
Debugging for bugs found on AWS test (1 day)
Update test plan (1 day)
Create test cases (1 day)
Update Top K DAO-
Top K next place report
(1 day)
Update Top K DAO –
Top K people report
(1 day)
Iteration 5 Critical Path: 11 days, Slack: 3 days
Demo of prototype and progress update (0.5 day)
UI – Improve Usability
(1 days)
Create Top K DAO -
Top K places
(1 day)
Develop JSON Heat Map
(1 days)
Develop JSON AGI
(1 days)
Top K reports debug
(1 days)
Develop JSON Top K
(1 days)
Redeployment on AWS for UAT(1 day)

## Slide 24
Design
Testing
Coding
Planning
Integration
Deployment
Overall functions testing and debugging
(2 days)
Enhance UI (3 days)
Integrate improved UI with previous functions (1 day)
Deployment on AWS
(1 day)
Post- UAT Improve application (3 days)
Manual UAT in class and automated UAT (1 day)
Testing and debugging after deployment
(1 day)
Final Presentation Slides (1 day)
Iteration 6 Critical Path: 11 days, Buffer: 3 days
Final Submission
(1 day)
Final Deployment on AWS
(1 day)

## Slide 25
Planning
Final presentation
(0.5 day)
Final presentation rehearsal
(0.5 day)
Iteration 7 Critical Path: 1 Days

## Slide 26: Metrics
Task metrics

## Slide 27: 4.1 Task Metric Results
Iteration | No. of Planned Tasks | Total no. of Tasks | Completed Tasks | Uncompleted Tasks | Result
1 | 10 | 12 | 12 | 0 | 1.2
2 | 18 | 20 | 15 | 5 | 0.83
3 | 24 | 28 | 22 | 6 | 0.92
4 | 31 | 31 | On going | On going | On going

## Slide 28: 4.2 Task Metric Graph
Lesson Learnt:
  With improvements made in task management after underloading in iteration 1 and overloading in iteration 2, we managed to keep our task metric between 90% to 110%

## Slide 29: 4.3 Burndown

## Slide 30: Metrics
bug Metrics

## Slide 31: 4.4 Bug Metric Results
Iteration | No. of low impact Bugs | No. of high impact bugs | No. of critical impact bugs | Total severity points | Bugs carried to next iteration
1 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 1 | 10 | 0
3 | 1 | 4 | 2 | 41 | 0
4 | 0 | 3 | 1 | 25 | On-going

## Slide 32: Roles and Responsibilities
Rotation plan

## Slide 33: 5.1 Task Distribution
Functions | Joel | Shreyas | Ming Xuan | Amanda | Joleen
Login Authentication |  |  |  |  | 
Bootstrap |  |  |  |  | 
Validations of csv files |  |  |  |  | 
Student breakdown report |  |  |  |  | 
Heat Map |  |  |  |  | 
Automated Group Identification |  |  |  |  | 
Dual Interface |  |  |  |  | 
Top k report |  |  |  |  | 
UI – Develop |  |  |  |  | 
UI – Improve Usability |  |  |  |  | 
UI – Enhance |  |  |  |  | 

## Slide 34: 5.2 Rotation Plan
Iteration | Week duration | PM | Pair Programming 1 | Pair Programming 2
1 | 2-3 | Joel | - | -
2 | 4-5 | Shreyas | Amanda, Joleen | Ming Xuan, Joel
3 | 6-7 | Amanda | Joel, Joleen | Ming Xuan, Shreyas
4 | 8-9 | Ming Xuan | Joel, Amanda | Shreyas, Joleen
5 | 10-11 | Joleen | Joel, Ming Xuan | Shreyas, Amanda
6 | 12-13 | Shreyas | Amanda, Joel | Ming Xuan, Joleen
7 | 14 | Joel | - | -

## Slide 35: 5.3 Current Work Hours Breakdown

## Slide 36: 5.4 Remaining PM Milestones
Supervisor Meeting 2 (25/10/2017) - Joleen
Application Demo and Progress Update (25/10/2017) – Joleen
UAT Deployment (5/11/2017) - Joleen
UAT In-class (8/11/2017) – Shreyas
Final Submission (19/11/2017) – Shreyas
Final Presentation (22/11/2017) – Joel

## Slide 37: THE END
G1T3