## Test Case for Login Validation
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
1 | Admin: correct name, correct password | username: admin password: AdminPW | Enter usename into username field and password into password field. Then submit | Login successful. Redirect to adminDashboard page | Login successful. Redirect to adminDashboard page | Pass | Pass | Pass
2 | Admin: correct name, wrong password | username: admin password: wrongpassword | Enter usename into username field and password into password field. Then submit. | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Pass | Pass | Pass
3 | Admin: correct name, empty password | username: admin password: | Enter usename into username field. Then submit. | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
4 | Admin: wrong name, correct password | username: wrongusername password: AdminPW | Enter wrong username and the right password into field. Then submit. | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Pass | Pass | Pass
5 | Admin: wrong name, wrong password | username: password: admin123 | Enter wrong username and empty password. Then submit. | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Pass | Pass | Pass
6 | Admin: empty name, empty password | username: password: | No username and password entered. Then submit. | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
7 | Admin: Special character name, empty password | username:%@$@#$@dd5555 password: | Enter special characters in username and empty pssword. Then submit | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
8 | Admin: same inputs for name, password | username: admin password: Admin | Enter same characters in username and password. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Login unsuccessful. Redirect back to login page with "Invalid user credentials" | Pass | Pass | Pass
9 | Admin: wrong name, empty password | username: admin2 password: | Enter wrong username and empty password. Then submit. | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
10 | Admin: empty name, correct password | username: password: AdminPW | Enter correct password but leave username field blank. Then submit | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | - | - | Pass
11 | Student enter correct credentials | username: aaravamuthan.pillay.2016 password: qwerty322 | Enter correct usename "aaravamuthan.pillay.2016" and correct password "qwerty322" . Then submit | Login successful. Redirect to studentDashboard page | Login successful. Redirect to studentDashboard page | Pass | Pass | Pass
12 | Student enter correct username and wrong password | username: aaravamuthan.pillay.2016 password: wrongpassword123 | Enter correct usename "aaravamuthan.pillay.2016" and wrong password "wrongpassword123" . Then submit | Login unsuccessful. Redirect back to login page with " Invalid user credentials" error message. | Login unsuccessful. Redirect back to login page with " Invalid user credentials" error message. | Pass | Pass | Pass
13 | Student enters correct username and empty password | username: aaravamuthan.pillay.2016 password: | Enter correct usename "aaravamuthan.pillay.2016" and empty password . Then submit | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
14 | Student enters wrong userename and wrong password | username: iamSIS password: qwerty128 | Enter wrong pass "iamSIS" and wrong password "qwerty128" into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Pass | Pass | Pass
15 | Student enters empty username and empty password | username: password: | Enter empty pass and empty password into password field. Then submit | Form doesn’t get passed in, page doesn’t submit | Form doesn’t get passed in, message "please fill out this field " appears | Pass | Pass | Pass
16 | Student enters empty username and correct password | username: password: qwerty322 | Enter empty usename and correct password "qwerty322" . Then submit | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Pass | Pass | Pass
17 | Student enters wrong username with correct password | username: IamSIS password: qwerty322 | Enter wrong pass "iamSIS" and wrong password "qwerty322" into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Login unsuccessful. Redirect back to login page with "Invalid username/password" error message. | Pass | Pass | Pass
18 | User tried to access Home.jsp | /home.jsp | User changes web URL directory to access home.jsp | Redirect back to login page. | Redirect back to login page. | Pass | Pass | Pass
19 | User tried to access Admin.jsp | /admin.jsp | User changes web URL directory to access admin.jsp | Redirect back to login page. | Redirect back to login page. | Pass | Pass | Pass
20 | User tried to access BreakdownReports.jsp | /BreakdownReports.jsp | User changes web URL directory to access BreakdownReports.jsp | Redirect back to login page. | Redirect back to login page. | - | Pass | Pass
21 | User tried to access BasicLocationReports.jsp | /BasicLocationReports.jsp | User changes web URL directory to access BasicLocationReports.jsp | Redirect back to login page. | Redirect back to login page. | - | Pass | Pass
22 | User tried to access TopkReports.jsp | /TopkReports.jsp | User changes web URL directory to access TopkReports.jsp | Redirect back to login page. | Redirect back to login page. | - | Pass | Pass
23 | User tried to access AutomaticGroupIdentification.jsp | /AutomaticGroupIdentification.jsp | User changes web URL directory to accessAutomaticGroupIdentification.jsp | Redirect back to login page. | Redirect back to login page. | - | Pass | Pass
24 | User tried to access HeatMaps.jsp | /HeatMaps.jsp | User changes web URL directory to access HeatMaps.jsp | Redirect back to login page. | Redirect back to login page. | - | Pass | Pass
25 | Admin: enters the right credentials, but both username and password in capital letters | username: ADMIN password: ADMINPW | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass
26 | Student: enters the right credentials, but both username and password in capital letters | username: AARAVAMUTHAN.PILLAY.2016 password: QWERTY322 | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass
27 | Admin: enters the right credentials, but username in capital letters | username: ADMIN password: adminPW | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass
28 | Student: enters the right credentials, but username in capital letters | username: AARAVAMUTHAN.PILLAY.2016 password: qwerty322 | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass
29 | Admin: enters the right credentials, but password in capital letters | username: Admin password: ADMINPW | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass
30 | Student: enters the right credentials, but password in capital letters | username: aaravamuthan.pillay.2016 password: QWERTY322 | Enter usename into username field and password into password field. Then submit | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | Login unsuccessful. Redirect back to login page with "Invalid user credentials". | - | Pass | Pass

## Test Case for Login Val JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | correct username, correct password | username: admin password: AdminPW | correct username and password inputs entered into the URL | Status: success Token: with a token being generated out | status: success Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTczMzQ2MiwiaWF0IjoxNTA5NzI5ODYyfQ.trRefyNgW-H7PaSY06HikZlbXL-Ga7b3DRuExhBXLUo] | Pass
2 | correct username, incorrect password | username: admin password: wrongpassword | correct username and incorrect password inputs entered into the URL | Status: error Error: invalid username/password | Status: error Error: invalid username/password | Pass
3 | incorrect username, correct password | username: wrongAdmin password: AdminPW | incorrect username and correct password inputs entered into the URL | Status: error Error: invalid username/password | Status: error Error: invalid username/password | Pass
4 | incorrect username, incorrect password | username: wrongAdmin password: wrongPassword | incorrect username and incorrect password inputs entered into the URL | Status: error Error: invalid username/password | Status: error Error: invalid username/password | Pass
5 | Blank username, blank password | username: " " password: " " | blank username and password inputs are entered into the URL | Status error Error: Blank username Blank password | Status error Error: Blank username Blank password | Pass
6 | Correct password, missing username | password: AdminPW | Correct password entered into the URL, and missing username in URL | Status: error Error: missing username | Status: error Error: missing username | Pass
7 | Correct username, missing password | username: admin | Correct username entered into the URL, and missing password in URL | Status: error Error: missing password | Status: error Error: missing password | Pass
8 | Correct username, blank password | username: admin password: " " | Correct username entered into the URL, and blank password in URL | Status: error Error: blank password | Status: error Error: blank password | Pass
9 | Blank username, correct password | username: " " password: AdminPW | Blank username entered into the URL, and correct password in URL | Status: error: Error: blank username | Status: error: Error: blank username | Pass
10 | Blank username, missing password | username: " " | Blank username entered into the URL, and missing password in URL | Status: error: Error: blank username missing password | Status: error: Error: blank username missing password | Pass
11 | Blank password, missing username | password: " " | Blank password entered into the URL, and missing username in URL | Status: error: Error: blank password missing username | Status: error: Error: blank password missing username | Pass

## Test Case for Bootstrap
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6
1 | Admin bootstraps a zip file containing "location.csv", "location-lookup.csv","demographic.csv" | data-se-v4.zip | Admin enters the admin.jsp and uploads a data-se-v4.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Pass | Pass
2 | Admin bootstraps a .mp4 file | this-testcase.mp4 | Admin enteres the admin.jsp and uploads this-test.mp4 file to see if the application crashes | Redirect to Admin DashBoard, database unchanged | Redirect to Admin DashBoard, database unchanged | Pass | Pass
3 | Admin bootstraps a .doc | this-testcase.doc | Admin enteres the admin.jsp and uploads this-test.doc file to see if the application crashes | Redirect to Admin DashBoard, database unchanged | Redirect to Admin DashBoard, database unchanged | Pass | Pass
4 | Admin bootstraps a .zip file containing multiple files with "demograph.csv" | this-mixcase.zip | Admin enters the admin.jsp and uploads a this-mixcase.zip file containing "demograph.csv" along with other irrelevant files to see if application processes the data | Redirect to Admin DashBoard, only location database updated, error messages shown | Redirect to Admin DashBoard, only demograph database updated, error messages shown | Pass | Pass
5 | Admin bootstraps a .zip file containing only "location-lookup.csv" | location-lookup.zip | Admin enters the admin.jsp and uploads a location-lookup.zip file containing "location-lookup.csv" to see if application processes the data | Redirect to Admin DashBoard, only locationlookup database updated, error messages shown | Redirect to Admin DashBoard, only locationlookup database updated, error messages shown | Pass | Pass
6 | Admin bootstraps a csv | location-lookup.csv | Admin enters the admin.jsp and uploads "location-lookup.csv" to see if application processes the data | Redirect to Admin DashBoard, database unchanged | Redirect to Admin DashBoard, database unchanged | Pass | Pass
7 | Admin bootstraps a zip file containing "location.csv", "location-lookup.csv","demographic.csv" and other csv files | this-allcsvcase.zip | Admin enters the admin.jsp and uploads this-allcsvcase.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Pass | Pass
8 | Admin bootstraps a zip file containing "location.csv", "location-lookup.csv","demographic.csv" but all files only have headers | headersonly.zip | Admin enters the admin.jsp and uploads headersonly.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard, database empty, no error msg | Redirect to Admin DashBoard, database empty, no error msg | Pass | Pass
9 | Admin bootstraps a zip file containing "location.csv", "location-lookup.csv","demographic.csv" but files contents are mixed up | mixed-up.csv | Admin enters the admin.jsp and uploads mixed-up.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard, database empty, error msgs for all rows | Redirect to Admin DashBoard, database empty, error msgs for all rows | Pass | Pass
10 | Admin bootstraps a zip file containing a folder that houses "location.csv", "location-lookup.csv","demographic.csv" | interloop.csv | Admin enters the admin.jsp and uploads a interloop.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Pass | Pass
11 | Admin bootstraps a zip file containing a zipfolder that houses "location.csv", "location-lookup.csv","demographic.csv" | zipinterloop.csv | Admin enters the admin.jsp and uploads a zipinterloop.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Redirect to Admin DashBoard, database empty, no error msg | Pass | Pass
12 | Admin bootstraps a zip file containing a folder structure that houses "location.csv", "location-lookup.csv","demographic.csv" in different levels | tierinterloop.csv | Admin enters the admin.jsp and uploads a tierinterloop.zip file containing "location.csv", "location-lookup.csv","demographic.csv" to see if application processes the data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Redirect to Admin DashBoard. Shows Error Messages, Database uploaded with sample data | Pass | Pass
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Test Case for Bootstrap JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | correct token, correct type of bootstrap file | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc3MjU3NiwiaWF0IjoxNTA5NzY4OTc2fQ.gkEW9qnllaj5iC14HlBJ7MZa7qjxaDuEBGyQ_vgk-JM] type of bootstrap file: Zip file for sample data | correct token and correct type of bootstrap file input into Postman. | Status: success With the numbers of rows loaded into the database from the the different sample data. Errors should also be output if there are any invalid data. | { "status": "error", "num-record-loaded": [ { "demographics.csv": 1670 }, { "location-lookup.csv": 270 }, { "location.csv": 481395 } ], "error": [ { "file": "demographics.csv", "line": 561, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 855, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 916, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1344, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1417, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1451, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1488, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1581, "message": [ "invalid email" ] } ] } | Pass
2 | correct token, wrong type of bootstrap file | Token [ eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc4MTA5NSwiaWF0IjoxNTA5Nzc3NDk1fQ.lJ14_HZIB_SeZV5_lbuddAZJWEoh8E240bnGh_kU_bg] Type of file: powerpoint slides | correct token and incorrect type of bootstrap file input into Postman. | Status: error Error: invalid file | { "status": "error", "messages": [ "invalid file" ] } | Pass
3 | incorrect token correct type of bootstrap file | Token: [incorrectToken] Type of file: sample data zip file | incorrect token and correct type of bootstrap file input into Postman. | Status: error Error: invalid token | { "status": "error", "messages": [ "invalid token" ] } | Pass
4 | incorrect token incorrect type of bootstrap file | Token [incorrectToken] | incorrect username and incorrect password inputs entered into the URL | Status: error Error: invalid token | { "status": "error", "messages": [ "invalid token" ] } | Pass
5 | Blank token, zip sample bootstrap file | token: "" Blank bootstrap zip file | Blank token and right type of bootstrap zip file input into Postman. | Status: error Error: Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
6 | Correct token, missing bootstrap file | Token:[eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc4NjA1NCwiaWF0IjoxNTA5NzgyNDU0fQ.0w3XpnN8SJgD9VIKS29o72I5CXU4vNlHWIOv6bBKzVA] missing bootstrap file | Correct token, and missing bootstrap zip file input into Postman. | Status: error Error: Missing file input | { "status": "error", "messages": [ "missing file input" ] } | Pass
7 | Blank token correct type of bootstrap file | Token: [] Correct type of zip sample data file | Blank token, and correct bootstrap zip file input into Postman. | Status: error Error:Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
8 | Blank token, missing bootstrap file | username: " " | Blank token, and missing bootstrap zip file input into Postman. | Status: error Error:Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
9 | Missing token, correct file | missing token correct type of zip sample data file | Missing token, and correct bootstrap zip file input into Postman. | Status: error Error: Missing token | { "status": "error", "messages": [ "missing token" ] } | Pass
10 | Correct token, correct file (specifically testing without any errors in sample data file) | Token: [ eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc5Nzc0NiwiaWF0IjoxNTA5Nzk0MTQ2fQ.lDaGZSv0ulmxd0uRzh3FkmcjXnuYMHXxMOmD09n4peE] Correct type of zip sample data file | Correct token, and correct bootstrap zip file input into Postman. | Status: success With the numbers of rows loaded into the database from the the different sample data. | { "status": "success", "num-record-loaded": [ { "demographics.csv": 8 }, { "location-lookup.csv": 270 }, { "location.csv": 128 } ] } | Pass
11 | Correct token, zip file with error in the demographics data. | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgwNTU1NCwiaWF0IjoxNTA5ODAxOTU0fQ.VJJC-FIp29zYGAKv3X2-q4qDkO-0Ni6yZWIwQFSWuz0] Zip file of sample data with an error in the demographics data | Correct token, and a sample data zip file input into Postman, with an error in demographics. | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid statement in demographics. | { "status": "error", "num-record-loaded": [ { "demographics.csv": 7 }, { "location-lookup.csv": 270 }, { "location.csv": 128 } ], "error": [ { "file": "demographics.csv", "line": 2, "message": [ "blank password", "blank email" ] } ] } | Pass
12 | Correct token, zip file with error in the location data. | Token:[eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgwNjI5NSwiaWF0IjoxNTA5ODAyNjk1fQ.rxwBpZFNR3ruQT4b09Jh91AMsDfoY6GOjs9e36eahNk] Zip file of sample data with an error in the location data | Correct token, and a sample data zip file input into Postman, with an error in location | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid statement in location | { "status": "error", "num-record-loaded": [ { "demographics.csv": 8 }, { "location-lookup.csv": 270 }, { "location.csv": 127 } ], "error": [ { "file": "location.csv", "line": 2, "message": [ "blank mac address", "blank location" ] } ] } | Pass
13 | Correct token, zip file with error in the location-lookup data. | Token:[eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNTQ0NywiaWF0IjoxNTA5ODMxODQ3fQ.FLRN8u1HfipUGdOi92N0CM8iX_1O65Zc4HLM3FVgmjU] Zip file of sample data with an error in the demographics data | Correct token, and a sample data zip file input into Postman, with an error in location-lookup. | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid statement in location- lookup. | { "status": "error", "num-record-loaded": [ { "demographics.csv": 8 }, { "location-lookup.csv": 269 }, { "location.csv": 128 } ], "error": [ { "file": "location-lookup.csv", "line": 2, "message": [ "blank semantic place" ] } ] } | Pass
14 | Correct token, with a wrong file uploaded | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNjUyNSwiaWF0IjoxNTA5ODMyOTI1fQ.8jHrt0yYJYAlXTNeL02enfcltByz-T8K6pMM-zX2lr0] Type of file: PNG | Correct token, and a wrong type of file uploaded. PNG file was uploaded instead. | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid file | { "status": "error", "num-record-loaded": [ { "demographics.csv": 1670 }, { "location-lookup.csv": 270 }, { "location.csv": 481395 } ], "error": [ { "file": "demographics.csv", "line": 561, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 855, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 916, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1344, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1417, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1451, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1488, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1581, "message": [ "invalid email" ] } ] } | Fail

## Test Case for Update JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | correct token, correct type of bootstrap file | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNTkzMywiaWF0IjoxNTA5ODMyMzMzfQ.p7-VxKEtPLzw7HFTHGLQridJA5FLmdK6CHO7af-7c-c] type of bootstrap file: Zip file for sample data 5 | correct token and correct type of bootstrap file input into Postman. | Status: success With the numbers of rows loaded into the database from the the different sample data. Errors should also be output if there are any invalid data. | { "status": "error", "num-record-loaded": [ { "demographics.csv": 1670 }, { "location.csv": 481395 } ], "error": [ { "file": "demographics.csv", "line": 561, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 855, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 916, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1344, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1417, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1451, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1488, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1581, "message": [ "invalid email" ] } ] } | Pass
2 | correct token, wrong type of bootstrap file | Token [ eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNTQ0NywiaWF0IjoxNTA5ODMxODQ3fQ.FLRN8u1HfipUGdOi92N0CM8iX_1O65Zc4HLM3FVgmjU] Type of file: powerpoint slides | correct token and incorrect type of bootstrap file input into Postman. | Status: error Error: invalid file | { "status": "error", "num-record-loaded": [ { "demographics.csv": 1670 }, { "location.csv": 481395 } ], "error": [ { "file": "demographics.csv", "line": 561, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 855, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 916, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1344, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1417, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1451, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1488, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1581, "message": [ "invalid email" ] } ] } * IT STILL GIVES OUT THE ROWS INVALID, but if you see close enough there is a change in the values | Fail
3 | incorrect token correct type of bootstrap file | Token: [incorrectToken] Type of file: sample data zip file | incorrect token and correct type of bootstrap file input into Postman. | Status: error Error: invalid token | { "status": "error", "messages": [ "invalid token" ] } | Pass
4 | incorrect token incorrect type of bootstrap file | Token [incorrectToken] Type of file: PNG | incorrect username and incorrect password inputs entered into the URL | Status: error Error: invalid token | { "status": "error", "messages": [ "invalid token" ] } | Pass
5 | Blank token, zip sample bootstrap file | token: "" Blank bootstrap zip file | Blank token and right type of bootstrap zip file input into Postman. | Status: error Error: Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
6 | Correct token, missing bootstrap file | Token:[eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc4NjA1NCwiaWF0IjoxNTA5NzgyNDU0fQ.0w3XpnN8SJgD9VIKS29o72I5CXU4vNlHWIOv6bBKzVA] missing bootstrap file | Correct token, and missing bootstrap zip file input into Postman. | Status: error Error: Missing file input | { "status": "error", "messages": [ "missing file input" ] } | Pass
7 | Blank token correct type of bootstrap file | Token: [] Correct type of zip sample data file | Blank token, and correct bootstrap zip file input into Postman. | Status: error Error:Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
8 | Blank token, missing bootstrap file | Token: '''" | Blank token, and missing bootstrap zip file input into Postman. | Status: error Error:Blank token | { "status": "error", "messages": [ "blank token" ] } | Pass
9 | Missing token, correct file | missing token correct type of zip sample data file | Missing token, and correct bootstrap zip file input into Postman. | Status: error Error: Missing token | { "status": "error", "messages": [ "missing token" ] } | Pass
10 | Correct token, correct file (specifically testing without any errors in sample data file) | Token: [ eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTc5Nzc0NiwiaWF0IjoxNTA5Nzk0MTQ2fQ.lDaGZSv0ulmxd0uRzh3FkmcjXnuYMHXxMOmD09n4peE] Correct type of zip sample data file | Correct token, and correct bootstrap zip file input into Postman. | { "status": "success", "num-record-loaded": [ { "demographics.csv": 8 }, { "location.csv": 128 } ] } | { "status": "success", "num-record-loaded": [ { "demographics.csv": 8 }, { "location.csv": 128 } ] } | Pass
11 | Correct token, zip file with error in the demographics data. | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNjUyNSwiaWF0IjoxNTA5ODMyOTI1fQ.8jHrt0yYJYAlXTNeL02enfcltByz-T8K6pMM-zX2lr0] Zip file of sample data with an error in the demographics data | Correct token, and a sample data zip file input into Postman, with an error in demographics. | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid statement in demographics. | { "status": "error", "num-record-loaded": [ { "demographics.csv": 7 }, { "location.csv": 128 } ], "error": [ { "file": "demographics.csv", "line": 2, "message": [ "blank password", "blank email" ] } ] } | Pass
12 | Correct token, zip file with error in the location data. | Token:[eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgwNjI5NSwiaWF0IjoxNTA5ODAyNjk1fQ.rxwBpZFNR3ruQT4b09Jh91AMsDfoY6GOjs9e36eahNk] Zip file of sample data with an error in the location data | Correct token, and a sample data zip file input into Postman, with an error in location | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid statement in location | { "status": "error", "num-record-loaded": [ { "demographics.csv": 8 }, { "location.csv": 127 } ], "error": [ { "file": "location.csv", "line": 2, "message": [ "blank mac address", "blank location" ] } ] } } | Pass
13 | Correct token, with a wrong file uploaded | Token: [eyJhbGciOiJIUzI1NiJ9.eyJzdWIiOiJBZG1pbiIsImV4cCI6MTUwOTgzNjUyNSwiaWF0IjoxNTA5ODMyOTI1fQ.8jHrt0yYJYAlXTNeL02enfcltByz-T8K6pMM-zX2lr0] Type of file: PNG | Correct token, and a wrong type of file uploaded. PNG file was uploaded instead. | Status: error With the number of rows loaded into the database from the sample data, as well as an error indicating that there is an invalid file | { "status": "error", "num-record-loaded": [ { "demographics.csv": 1670 }, { "location-lookup.csv": 270 }, { "location.csv": 481395 } ], "error": [ { "file": "demographics.csv", "line": 561, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 855, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 916, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1344, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1417, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1451, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1488, "message": [ "invalid email" ] }, { "file": "demographics.csv", "line": 1581, "message": [ "invalid email" ] } ] } | Fail
14

## Test Case for Student breakdown
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 4 | Iteration 5 | Iteration 6
1 | User: 1 Option selected, Correct time, Correct date | Option 1: Year/Gender/School Time: 11:15:00 AM Date: 06-02-2017 | Fill in option 1 from drop-down list, enter time into time field and enter date under date field, press button to submit | Display breakdown report of user search based on option selected within the specified time window | Display breakdown report of user search based on option selected within the specified time window | Pass | Pass
2 | User: 1 Option selected, Wrong time, Correct date | Option 1: Year/Gender/School Time: 25:00:02 AM Date: 06-02-2017 | Fill in option 1 from drop-down list, enter time into time field and enter date under date field, press button to submit | Error prompt on wrong date/time input | Error prompt on wrong date/time input | Pass | Pass
3 | User: 1 Option selected, Correct time, Wrong date | Option 1: Year/Gender/School Time: 11:15:00 AM Date: 06-13-2017 | Fill in option 1 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow wrong input of date | Form doesn’t allow wrong input of date | Pass | Pass
4 | User: 2 different options selected, Correct time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Time: 11:15:00 AM Date: 06-02-2017 | Fill in option 1 and 2 from drop-down list, enter time into time field and enter date under date field, press button to submit | Display breakdown report of user search based on option selected within the specified time window | Display breakdown report of user search based on option selected within the specified time window | Pass | Pass
5 | User: 2 different options selected, Wrong time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Time: 25:00:02 AM Date: 06-02-2017 | Fill in option 1 and 2 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow wrong input of time | Form doesn’t allow wrong input of time | Pass | Pass
6 | User: 2 different options selected, Correct time, Wrong date | Option 1: Year/Gender/School Option 2: Year/Gender/School Time: 11:15:00 AM Date: 06-13-2017 | Fill in option 1 and 2 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow wrong input of date | Form doesn’t allow wrong input of date | Pass | Pass
7 | User: 2 clashing options selected, Correct time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Time: 11:15:00 AM Date: 06-02-2017 | Fill in option 1 from drop-down list, fill in option 2 with the same option as 1 from the dropdown list, enter time into time field and enter date under date field, press button to submit | Error prompt on clashing option choice | Error prompt on clashing option choice | Pass | Pass
8 | User: 3 different options selected, Correct time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Option 3: Year/Gender/School Time: 11:15:00 AM Date: 06-02-2017 | Fill in option 1, 2 and 3 from drop-down list, enter time into time field and enter date under date field, press button to submit | Display breakdown report of user search based on option selected within the specified time window | Display breakdown report of user search based on option selected within the specified time window | Pass | Pass
9 | User: 3 different options selected, Wrong time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Option 3: Year/Gender/School Time: 25:00:02 AM Date: 06-02-2017 | Fill in option 1, 2 and 3 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow wrong input of time | Form doesn’t allow wrong input of time | Pass | Pass
10 | User: 3 different options selected, Correct time, Wrong date | Option 1: Year/Gender/School Option 2: Year/Gender/School Option 3: Year/Gender/School Time: 11:15:00 AM Date: 06-13-2017 | Fill in option 1, 2 and 3 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow wrong input of date | Form doesn’t allow wrong input of date | Pass | Pass
11 | User: 2 or more clashing options selected, Correct time, Correct date | Option 1: Year/Gender/School Option 2: Year/Gender/School Option 3: Year/Gender/School Time: 11:15:00 AM Date: 06-02-2017 | Fill in 2 or more options from dropdown list with same specifications, enter time into time field and enter date under date field, press button to submit | Error prompt on clashing option choice | Error prompt on clashing option choice | Pass | Pass
12 | User: 1 Option selected, Correct time, invalid date | Option 1: Year/Gender/School Time: 11:15:00 AM Date: 06-02-201722 | Fill in option 1 from drop-down list, enter time into time field and enter date under date field, press button to submit | Form doesn’t allow date more than 2025, date becomes 1722, empty results returned | Form doesn’t allow date more than 2025, date becomes 1722, empty results returned | Pass | Pass
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Test Case for Student bd JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct order, correct date, correct token | order: year,gender,school date: 2017-02-06T11:15:00 token: [token value] | All inputs are within the expected range (no error) | Breakdown report should be generated according to the given parameters | Breakdown report is generated according to the given parameters | Pass
2 | Correct order, correct date, incorrect token | order: year,gender,school date: 2017-02-06T11:15:00 token: randomstring!!! | Token is a random string | Error message: invalid token | Error message: invalid token | Pass
3 | Correct order, correct date, blank token | order: year,gender,school date: 2017-02-06T11:15:00 token: | Token is missing | Error message: blank token | Error message: blank token | Pass
4 | Correct order, correct date, missing token | order: year,gender,school date: 2017-02-06T11:15:00 | Token is blank | Error message: missing token | Error message: missing token | Pass
5 | Correct order, incorrect date, correct token | order: year,gender,school date: 2017-02-06 11:15:00 token: [token value] | 'T' missing | Error message: invalid date | Error message: invalid date | Pass
6 | Correct order, incorrect date, correct token | order: year,gender,school date: 1234567890 token: [token value] | Date is a random string with less than 11 characters | Error message: invalid date | Error message: invalid date | Pass
7 | Correct order, incorrect date, correct token | order: year,gender,school date: 12345678901 token: [token value] | Date is a random string 11 characters or more | Error message: invalid date | Error message: invalid date | Pass
8 | Correct order, incorrect date, correct token | order: year,gender,school date: 2017-02-06T11:115:00 token: [token value] | Date has an extra integer in minutes | Error message: invalid date | Error message: invalid date | Pass
9 | Correct order, incorrect date, correct token | order: year,gender,school date: 2017-02-06T11:15:001 token: [token value] | Date has an extra integer in seconds | Error message: invalid date | Error message: invalid date | Pass
10 | Correct order, missing date, correct token | order: year,gender,school date: token: [token value] | Date is blank | Error message: blank date | Error message: blank date | Pass
11 | Correct order, blank date, correct token | order: year,gender,school token: [token value] | Date is missing | Error message: missig date | Null pointer exception | Fail
12 | Incorrect order, correct date, correct token | order: randomstring!!!! date: 2017-02-06T11:15:00 token: [token value] | Order contains a random string | Error message: invalid order | Error message: invalid order | Pass
13 | Incorrect order, correct date, correct token | order: ,year, date: 2017-02-06T11:15:00 token: [token value] | Order contains valid option(s) but incorrectly placed commas (included preceeding commas) | Error message: invalid order | Error message: invalid order | Pass
14 | Incorrect order, correct date, correct token | order: ,,,,year date: 2017-02-06T11:15:00 token: [token value] | Order contains valid option(s) but trailing commas | Error message: invalid order | Error message: invalid order | Pass
15 | Incorrect order, correct date, correct token | order: year,,,, date: 2017-02-06T11:15:00 token: [token value] | Order contains valid option(s) but trailing commas | Error message: invalid order | Error message: invalid order | Pass
16 | Incorrect order, correct date, correct token | order: year,cat,dog date: 2017-02-06T11:15:00 token: [token value] | Order contains valid option(s) but trailing commas | Error message: invalid order | Error message: invalid order | Pass
17 | Incorrect order, correct date, correct token | order: year.school. date: 2017-02-06T11:15:00 token: [token value] | Order contains valid option(s) but wrong separator | Error message: invalid order | Error message: invalid order | Pass
18 | Blank order, correct date, correct token | order: date: 2017-02-06T11:15:00 token: [token value] | Order is blank | Error message: blank order | Error message: blank order | Pass
19 | Missing order, correct date, correct token | date: 2017-02-06T11:15:00 token: [token value] | Order is missing | Error message: missing order | Error message: missing order | Pass

## Test Case for AGD
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 4 | Iteration 5 | Iteration 6
1 | user: Valid day, valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 06-02-2017 and 10.15 AM with 0 seconds | Response, members, locations should be sorted according to requirements. Total time should be in seconds | Response, members, locations should be sorted according to requirements. Total time should be in seconds [n students, n groups. Group size, students in group and location timing all accounted] | Pass | Pass
2 | user: Valid day, invalid minute | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 06-02-2017 and 12:97 AM with 0 seconds | Form should not allow invalid time format (hours within 00 - 12, minutes within 00-59) | Form did not allow invalid time format, time became 12:09AM | Pass | Pass
3 | user: Valid day, invalid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 06-02-2017 and 41.15 AM with 0 seconds | Form should not allow invalid time format (hours within 00 - 12, minutes within 00-59) | Form did not allow invalid time format, time became 04:01AM | Pass | Pass
4 | user: Invalid day, valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 32-02-2017 and 10.15 AM with 0 seconds | Form should not allow invalid time format (day within 00 - 31, month within 00-12) | Form did not allow invalid time format, date became 31-02-2017 | Pass | Pass
5 | user: Invalid month valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-13-2017 and 10.15 AM with 0 seconds | Form should not allow invalid time format (day within 00 - 31, month within 00-12) | Form did not allow invalid time format, date became 31-12-2017 | Pass | Pass
5 | user: Invalid year valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-13-abcd and 10.15 AM with 0 seconds | Form should not allow invalid time format (day within 00 - 31, month within 00-12) | Form did not allow invalid time format, year not updated | Pass | Pass
6 | user: Invalid year valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-13-201a and 10.15 AM with 0 seconds | Form should not allow invalid time format (day within 00 - 31, month within 00-12) | Form did not allow invalid time format, year becomes 0201 | Pass | Pass
7 | user: Invalid year valid hour | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-11-123456 and 10.15 AM with 0 seconds | Form should not allow invalid time format (day within 00 - 31, month within 00-12, year within 0000-9999) | Form did not allow invalid time format, year becomes 2345 (max 4 digit) | Fail | Pass
8 | user: Valid day, valid hour (Future timing) | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-12-2020 and 10.15 AM with 0 seconds | Response, members, locations should be sorted according to requirements. No records of groups | Output : 0 students 0 groups | Fail | Pass
9 | user: Valid day, valid hour (very old timing) | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-12-1234 and 10.15 AM with 0 seconds | Response, members, locations should be sorted according to requirements. No records of groups | Output : 0 students 0 groups | Fail | Pass
10 | user: Valid day, missing time | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 06-02-2017 and unfilled time with 0 seconds | Form not sent, messages pops up to show to fill in value | Error msg appeared "Please fill in this field" | Fail | Pass
11 | user: Valid time, missing date | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter unfilled and 1015 AM with 0 seconds | Form not sent, messages pops up to show to fill in value | Error msg appeared "Please fill in this field" | Fail | Pass
12 | user: Valid time, invalid date | day in DD-MM-YYYY format, hour in HH:MM:SS format | Enter date 31-02-2017 and 10.15 AM with 0 seconds | Form not sent, messages pops up to show to fill in value | Error msg appeared "Please enter a valid value" | Pass | Pass
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Test Case for AGD JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct Token, Correct Date (Within data parameters) | Token: [token value] Date: 2017-02-06T10:15:00 | Users input a desired date and valid token | Json outputs status: success, the total number of users, the total number of groups and groups in the SIS building at a give date/time based on users' location trace (Sorted in the following order: size, total-time-spent (json attribute values), followed by members.) | Json outputs status: success, the total number of users, the total number of groups and groups. (output sorted in the following order: size, total-time-spent (json attribute values), followed by members.) | Pass
2 | Correct Token and blank Date | Token : [token value] Date : | Users input a blank date and valid token | Json outputs: Status: error, with error messages displayed | Json outputs:{ "status": "error", "messages": [ "blank date" ] } | Pass
3 | Correct Token and incorrect Date format | Token : [token value] Date : 02-06-2017T10:15:00 | Users input an incorrect date format and valid token | Json outputs: Status: error, with error messages displayed | Json outputs:{ "status": "error", "messages": [ "invalid date" ] } | Pass
4 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-13-02T10:15:00 | Users input an incorrect date (13 is not a valid month) and valid token | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date" ] } | Pass
5 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-02-45T10:15:00 | Users input an incorrect date 45 is not a valid day and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
5 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-12-06T99:00:00 | Users input an incorrect time format and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
6 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-12-06T10:15:005555 | Users input an incorrect time format and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
7 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-02-31T10:15:00 | Users input an incorrect time format and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
8 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-12-06T09:79:00 | Users input an incorrect time format and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
9 | Correct Token and incorrect Date format | Token : [token value] Date : 2017-02-06T11111:11111:11111 | Users input an incorrect time format and valid token | Json outputs: Status: error, with error messages displayed | Json Outputs : { "status": "error", "messages": [ "invalid date" ] } | Pass
10 | Correct Token and missing date | Token : [token value] | Users input an incorrect token and valid token | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "missing date" ] } | Pass
11 | Blank Token and Date | Token : Date : | Users input a blank date and token | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "missing token" ] } | Pass
12 | Blank Token and Correct Date | Token : Date : 2017-02-06T10:15:00 | Users input a blank token and correct date | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "blank token" ] } | Pass
13 | Blank Token and incorrect Date format | Token : Date : 02-06-2017T10:15:00 | Users input an incorrect date format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
14 | Blank Token and incorrect Date format | Token : Date : 2017-13-02T10:15:00 | Users input an incorrect date (13 is not a valid month) | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
15 | Blank Token and incorrect Date format | Token : Date : 2017-02-45T10:15:00 | Users input an incorrect date 45 is not a valid day | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
16 | Blank Token and incorrect Date format | Token : Date : 2017-02-45T10:15:00 | Users input an incorrect date 45 is not a valid day | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
17 | Blank Token and incorrect Date format | Token : Date : 2017-02-06T99:99:99 | Users input an incorrect time format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
18 | Blank Token and incorrect Date format | Token : Date : 2017-02-06T11111:11111:11111 | Users input an incorrect time format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "blank token" ] } | Pass
19 | Blank Token and missing date | Token : | Users input an incorrect token | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "missing date", "blank token" ] } | Pass
20 | Missing Token and Date |  | Users does not input a date and token | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "missing date", "missing token" ] } | Pass
21 | Missing Token and Correct Date | Token : Date : 2017-02-06T10:15:00 | Users input a blank token and correct date | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ missing token" ] } | Pass
22 | Missing Token and incorrect Date format | Token : Date : 02-06-2017T10:15:00 | Users input an incorrect date format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
23 | Missing Token and incorrect Date format | Token : Date : 2017-13-02T10:15:00 | Users input an incorrect date (13 is not a valid month) | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
24 | Missing Token and incorrect Date format | Token : Date : 2017-02-45T10:15:00 | Users input an incorrect date 45 is not a valid day | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
25 | Missing Token and incorrect Date format | Token : Date : 2017-02-45T10:15:00 | Users input an incorrect date 45 is not a valid day | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
26 | Missing Token and incorrect Date format | Token : Date : 2017-02-06T99:99:99 | Users input an incorrect time format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
27 | Missing Token and incorrect Date format | Token : Date : 2017-02-06T11111:11111:11111 | Users input an incorrect time format | Json outputs: Status: error, with error messages displayed | Json outputs: { "status": "error", "messages": [ "invalid date", "missing token" ] } | Pass
28 | Correct Token, Correct Date , additional parameters (Within data parameters) | Token: [token value] Date: 2017-02-06T10:15:00 Additional: ThisIsAAdditionalInput | Users input a desired date and valid token but keys in an extra input parameter | Json outputs status: success, the total number of users, the total number of groups and groups in the SIS building at a give date/time based on users' location trace (Sorted in the following order: size, total-time-spent (json attribute values), followed by members.) | Json outputs status: success, the total number of users, the total number of groups and groups. (output sorted in the following order: size, total-time-spent (json attribute values), followed by members.) | Pass
29
30

## Test Case for HeatMap
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 4 | Iteration 5 | Iteration 6
1 | User: Selects floor, correct time, correct date | Floor: Basement 1 Time: 11:15:00 AM Date: 06-02-2017 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays B1 floorplan as well as the heat density of the location with legends | Pass | Pass
2 | User: Selects floor, correct time, correct date | Floor: Level 1 Time: 11:15:00 AM Date: 06-02-2018 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays Level 1 floorplan as well as the heat density of the location with legends | Pass | Pass
3 | User: Selects floor, correct time, correct date | Floor: Level 2 Time: 11:15:00 AM Date: 06-02-2019 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays Level 2 floorplan as well as the heat density of the location with legends | Pass | Pass
4 | User: Selects floor, correct time, correct date | Floor: Level 3 Time: 11:15:00 AM Date: 06-02-2020 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays Level 3 floorplan as well as the heat density of the location with legends | Pass | Pass
5 | User: Selects floor, correct time, correct date | Floor: Level 4 Time: 11:15:00 AM Date: 06-02-2021 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays Level 4 floorplan as well as the heat density of the location with legends | Pass | Pass
6 | User: Selects floor, correct time, correct date | Floor: Level 5 Time: 11:15:00 AM Date: 06-02-2022 | User selects a desired floor from list, and then inputs a valid time and date and submits form | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Web Interfaces displays Level 5 floorplan as well as the heat density of the location with legends | Pass | Pass
7 | User: Selects floor, wrong time, correct date | Floor: Basement 1 Time: 11:98:00 AM Date: 06-02-2017 | User selects a desired floor from list, and then inputs an invalid time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
8 | User: Selects floor, blank time, correct date | Floor: Basement 1 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
9 | User: Selects floor, incomplete time, correct date | Floor: Basement 1 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
10 | User: Selects floor, correct time, wrong date | Floor: Basement 1 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
11 | User: Selects floor, correct time, blank date | Floor: Basement 1 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
12 | User: Selects floor, correct time, incomplete date | Floor: Basement 1 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
13 | User: Selects floor, blank time, correct date | Floor: Level 1 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
14 | User: Selects floor, incomplete time, correct date | Floor: Level 1 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
15 | User: Selects floor, correct time, wrong date | Floor: Level 1 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
16 | User: Selects floor, correct time, blank date | Floor: Level 1 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
17 | User: Selects floor, correct time, incomplete date | Floor: Level 1 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
18 | User: Selects floor, blank time, correct date | Floor: Level 2 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
19 | User: Selects floor, incomplete time, correct date | Floor: Level 2 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
20 | User: Selects floor, correct time, wrong date | Floor: Level 2 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
21 | User: Selects floor, correct time, blank date | Floor: Level 2 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
22 | User: Selects floor, correct time, incomplete date | Floor: Level 2 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
23 | User: Selects floor, blank time, correct date | Floor: Level 3 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
24 | User: Selects floor, incomplete time, correct date | Floor: Level 3 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
25 | User: Selects floor, correct time, wrong date | Floor: Level 3 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
26 | User: Selects floor, correct time, blank date | Floor: Level 3 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
27 | User: Selects floor, correct time, incomplete date | Floor: Level 3 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
28 | User: Selects floor, blank time, correct date | Floor: Level 4 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
29 | User: Selects floor, incomplete time, correct date | Floor: Level 4 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
30 | User: Selects floor, correct time, wrong date | Floor: Level 4 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
31 | User: Selects floor, correct time, blank date | Floor: Level 4 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
32 | User: Selects floor, correct time, incomplete date | Floor: Level 4 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
33 | User: Selects floor, blank time, correct date | Floor: Level 5 Time: Date: 06-02-2018 | User selects a desired floor from list, and then inputs a blank time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
34 | User: Selects floor, incomplete time, correct date | Floor: Level 5 Time: 11:--:-- -- Date: 06-02-2019 | User selects a desired floor from list, and then inputs an incomplete time and valid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
35 | User: Selects floor, correct time, wrong date | Floor: Level 5 Time: 11:15:00 AM Date: 06-13-2017 | User selects a desired floor from list, and then inputs an valid time and invalid date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
36 | User: Selects floor, correct time, blank date | Floor: Level 5 Time: 11:15:00 AM Date: | User selects a desired floor from list, and then inputs an valid time and blank date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass
37 | User: Selects floor, correct time, incomplete date | Floor: Level 5 Time: 11:15:00 AM Date: 06/mm/yyyy | User selects a desired floor from list, and then inputs an valid time and incomplete date and submits form | Error message for invalid date/time | Web Interface displays error msg "Invalid date-time format" | Pass | Pass

## Test Case for HeatMap JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct token, correct floor, correct date | Token: [token value] Floor:5 Date: 2017-06-02T11:15:00 | Users input a desired floor and date | HeatMap results are displayed based on the floor and crowd density derived from the date time input | HeatMap results are displayed based on the floor and crowd density derived from the date time input | Pass
2 | Correct token, Correct floor, Blank date | Token: [token value] Floor:5 Date: | Blank date | Error message: Blank date | Error message: Blank date | Pass
3 | Correct token, Correct floor, Missing date | Token: [token value] Floor:5 | Missing date | Error message: Missing date | Error message: Missing date | Pass
4 | Correct token, Correct floor, wrong date | Token: [token value] Floor:5 Date: 17-06-02T11:15:00 | Incorrect year format | Error message: Invalid date | Error message: Invalid date | Pass
5 | Correct token, Correct floor, wrong date | Token:[token value] Floor:5 Date: 2017-6-02T11:15:01 | Incorrect month format | Error message: Invalid date | Error message: Invalid date | Pass
6 | Correct token, Correct floor, wrong date | Token:[token value] Floor:5 Date: 2017-06-2T11:15:02 | Incorrect day format | Error message: Invalid date | Error message: Invalid date | Pass
7 | Correct token, Correct floor, wrong date | Token: [token value] Floor:2 Date: datetime | Random string | Error message: Invalid date | Error message: Invalid date | Pass
8 | Correct token, Correct floor, wrong date | Token: [token value] Floor:2 Date: 06-02-2017 11:15:01 | T' missing | Error message: Invalid date | Error message: Invalid date | Pass
9 | Correct token, Correct date, blank floor | Token: [token value] Floor: Date: 06-02-2017T11:15:02 | Blank floor | Error message: Blank floor | Error message: Blank floor | Pass
10 | Correct token, Correct date, Missing floor | Token: [token value] Date: 06-02-2017T11:15:03 Floor: | Missing floor | Error message: Missing floor | Error message: Missing floor | Pass
11 | Correct token, Correct date, wrong floor | Token: [token value] Floor:10 Date: 06-02-2017T11:15:03 | Index out of range | Error message: Invalid floor | Error message: Invalid floor | Pass
12 | Correct token, Correct date, wrong floor | Token:[token value] Floor:Ten Date: 06-02-2017T11:15:04 | Random string | Error message: Invalid floor | Error message: Invalid floor | Pass
13 | Correct date, correct floor, incorrect token | Token: khehdbsk Floor:4 Date: 06-02-2017T11:15:05 | Random string | Error message: Invalid token | Error message: Invalid token | Pass
14 | Correct date, correct floor, incorrect token | Token: Floor:4 Date: 06-02-2017T11:15:06 | Empty token | Error message: Blank token | Error message: Blank token | Pass
15 | Correct date, correct floor, no token | Floor:4 Date: 06-02-2017T11:15:07 | Missing token | Error message: Missing token | Error message: Missing token | Pass
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Test Case for TopKPopularP
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | User: Selects correct time, correct date, correct k | Time: 11:15 AM Date: 06/02/2017 k = 3 | Users inputs a valid time, valid k, valid k and submits form | Top-k popular places results are displayed based on the time and date the user select | Displays top k popular places | Pass
2 | User: Selects correct time, correct k, wrong date | Time: 11:15 AM Date: 06/02/201789 k = 4 | Users inputs a valid time, valid k and out of range year and submits form | Empty result set | Empty result set | Pass
3 | User: Selects correct time, correct k, wrong date | Time: 11:15 AM Date: 06/02/a003 k = 5 | Users inputs a valid time, valid k, invalid year and submits form | Form did not allow invalid year format | Form did not allow invalid year format | Pass
4 | User: Selects correct time, correct k, wrong date | Time: 11:15 AM Date: 06/h2/2019 k = 6 | Users inputs a valid time, valid k, invalid month and submits form | Form did not allow invalid month format | Form did not allow invalid month format | Pass
5 | User: Selects correct time, correct k, wrong date | Time: 11:15 AM Date: 0g/02/2019 k = 7 | Users inputs a valid time, valid k, invalid day and submits form | Form did not allow invalid day format | Form did not allow invalid day format | Pass
6 | User: Selects correct time, correct k, wrong date | Time: 11:15 AM Date: 31/02/2017 k = 6 | User input a correct time, correct origin, and a non-exsistent day in Feburary | Form prompted Invalid date entered | Form prompted Invalid date entered | Pass
7 | User: Selects empty time, empty date, correct k | Time: --:-- -- Date: --/--/---- k = 8 | Users inputs an empty time, empty date and correct k and submits form | Form did not allow empty time and empty date to be submitted | Form did not allow empty time and empty date to be submitted | Pass
8 | User: Selects empty time, correct date, correct k | Time: --:-- -- Date: 06/02/2017 k = 9 | Users inputs an empty time, empty date and correct k and submits form | Form did not allow empty time to be submitted | Form did not allow empty time and empty date to be submitted | Pass
9 | User: Selects correct time, correct k, empty date | Time: 11:11 PM Date: --/--/---- k = 10 | Users inputs an empty time, empty date and correct k and submits form | Form did not allow empty date to be submitted | Form did not allow empty time and empty date to be submitted | Pass
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39

## Test Case for TopKPP JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct token, correct K value, correct date | Token: [token value] K = 3 Date: 2017-06-02T11:15:00 | Users input a desired K value and date | Top K popular places are displayed based on the date time window indicated | Top K popular places are displayed based on the date time window indicated | Pass
2 | Correct token, correct K value, blank date | Token: [token value] K = 3 Date: | blank date | Error message: Blank date | Error message: Blank date | Pass
3 | Correct token, correct K value, missing date | Token: [token value] K = 3 | Missing date | Error message: Missing date | Error message: Missing date | Pass
4 | Correct token, blank K value, correct date | Token: [token value] K = Date: 2017-06-02T11:15:00 | Blank K | Error message: Blank K | Error message: Blank K | Pass
5 | Correct token, missing K value, correct date | Token: [token value] Date: 2017-06-02T11:15:00 | Missing K | K is assumed to be 3, report generates | K is assumed to be 3, report generates | Pass
6 | Correct token, correct K value, Wrong date | Token: [token value] K = 3 Date: 2017-06-2T11:15:02 | Incorrect day format | Error message: Invalid date | Error message: Invalid date | Pass
7 | Correct token, correct K value, Wrong date | Token: [token value] K = 3 Date: datetime | Random string replaces date | Error message: Invalid date | Error message: Invalid date | Pass
8 | Correct token, correct K value, Wrong date | Token: [token value] K = 3 Date: 2017-06-02 11:15:00 | T' missing | Error message: Invalid date | Error message: Invalid date | Pass
9 | Correct token, correct K value, Wrong date | Token: [token value] K = 3 Date: 11:15:00T2017-06-02 | Date Time swap positions | Error message: Invalid date | Error message: Invalid date | Pass
10 | Correct token, wrong K value, correct date | Token: [token value] K = 11 Date: 06-02-2017T10:15:00 | K Index out of range positive | Error message: Invalid K | Error message: Invalid K | Pass
11 | Correct token, wrong K value, correct date | Token: [token value] K = -1 Date: 06-02-2017T10:15:00 | K Index out of range negative | Error message: Invalid K | Error message: Invalid K | Pass
12 | Correct token, Incorrect K, Correct Date | Token: [token value] K = three Date: 06-02-2017T10:15:00 | Random string K Value | Error message: Invalid K | Error message: Invalid K | Pass
13 | Incorrect token, Correct K, Correct Date | Token: hello K = 3 Date = 06-02-2017T10:15:00 | Random String token | Error message: Invalid token | Error message: Invalid token | Pass
14 | Incorrect token, Correct K, Correct Date | Token: K = 3 Date = 06-02-2017T10:15:00 | Empty token | Error message: Blank token | Error message: Blank token | Pass
15 | Incorrect token, Correct K, Correct Date | K = 3 Date = 06-02-2017T10:15:00 | Missing token | Error message: Missing token | Error message: Missing token | Pass
16 | Incorrect Token, Incorrect K, Incorrect Date | Token: 123 K = -1 Date = 06-02-2017T10:15 | Wrong Token, Wrong K, Wrong Date | Error message: Invalid K, Invalid Date, Invalid Token | Error message: Invalid K, Invalid Date, Invalid Token | Pass
17 | Correct token, Incorrect K, Incorrect Date | Token: [token value] K = -1 Date = 06-02-2017T10:15 | Index out of range K value and wrong date | Error Message: Invalid Date, Invalid K | Error Message: Invalid Date, Invalid K | Pass
18 | Incorrect token, Correct K, Incorrect Date | Token: 1234 K = 3 Date = 06-02-2017T10:15 | Wrong Token, Wrong date | Error Message: Invalid Date, Invalid Token | Error Message: Invalid Date, Invalid Token | Pass
19 | Incorrect token, Incorrect K, Correct Date | Token: 1234 K = -1 Date = 06-02-2017T10:15:00 | Wrong token, Index out of range K value | Error Message: Invalid K, Invalid Token | Error Message: Invalid K, Invalid Token | Pass
20 | Correct token, Incorrect K, Correct Date | Token: [token value] K = 3.3 Date: 06-02-2017T10:15:00 | K Value decimal | Error message: Invalid K | Error message: Invalid K | Pass

## Test Case for TopKNextPlaces
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | User: Select correct k correct date, correct time, correct origin | k: 3 date: 02/06/2017 time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and correct date | Top k next places are displayed based on the percentage, date, time and origin indicated | Top k next places are displayed based on the percentage, date, time and origin indicated | Pass
2 | User: Select correct k correct time, correct origin, invalid date range | k: 3 date: 02/06/201797 time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and wrong year format | Error message: Invalid date | Error message: Invalid date | Pass
3 | User: Select correct k correct time, correct origin, invalid date range | k: 3 date: 02/12/903h time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and wrong year format | Form did not allow invalid year format | Form did not allow invalid year format | Pass
4 | User: Select correct k correct time, correct origin, invalid date range | k: 3 date: 02/30/2017 time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and a non-exsistent day in Feburary | Form prompted Invalid date entered | Form prompted Invalid date entered | Pass
5 | User: Select correct k,correct time, correct origin, invalid date | k: 3 date: 01/aa/2017 time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and a month format in alphabets | Form did not allow invalid month format | Form did not allow invalid month format | Pass
6 | User: Select correct k correct time, correct origin, invalid date | k: 3 date: aa/18/2017 time: 10:20 AM origin: SMUSISL2LiftLobby | User input a correct k,correct time, correct origin, and a day format in alphabets | Form did not allow invalid date format | Form did not allow invalid date format | Pass
7 | User: Select correct k correct time, correct origin, correct date invalid time range | k: 3 date: 06/18/2017 time: aa:15 AM origin: SMUSISL2LiftLobby | User input a correct k,correct date, correct origin, and a wrong time with alphabets | Form did not allow invalid time format | Form did not allow invalid time format | Pass
8 | User: Select correct k, correct origin, correct date, empty time | k: 3 date: 06/18/2017 time: --:-- origin: SMUSISL2LiftLobby | User input a correct k,correct date, correct origin, and an empty time | Form did not allow out of range time format | Form did not allow out of range time format | Pass
9 | User: Select correct k, correct origin, correct time empty date | k: 3 date: --/--/---- time: 90:20 origin: SMUSISL2LiftLobby | User input a correct k, correct origin, correct time, empty date | Form did not allow out of range time format | Form did not allow out of range time format | Pass
10 | User: Select correct k, correct origin, empty time, empty date | k: 3 date: --/--/---- time: --:-- origin: SMUSISL2LiftLobby | User input a correct k, correct origin, empty time, empty date | Form did not allow out of range time format | Form did not allow out of range time format | Pass
11

## Test Case for TopKNextP JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct token, origin and date , missing k | Token: [token value] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 | Correct token, origin and date input into the URL. | Status: success, with the different ranks [Default: 3], next places and time together being displayed. | { "status": "success", "total-users": 31, "total-next-place-users": 28, "results": [ { "rank": 1, "semantic-place": "SMUSISL1ReceptionAndLobby", "count": 11 }, { "rank": 2, "semantic-place": "SMUSISL2LiftLobby", "count": 3 }, { "rank": 2, "semantic-place": "SMUSISL2StudyArea1", "count": 3 }, { "rank": 3, "semantic-place": "SMUSISL4LiftLobby", "count": 2 } ] } | Pass
2 | Invalid token, correct origin and date , missing k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 | Correct origin and date input, invalid token into the URL. | Status error, invalid token message appears | { "status": "error", "messages": [ "invalid token" ] } | Pass
3 | Invalid token, origin and correct date , missing k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:01 | Correct date input, invalid token and origin into the URL. | Status error, invalid token, origin message appears | { "status": "error", "messages": [ "invalid origin", "invalid token" ] } | Pass
4 | Invalid token, origin and date , missing k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:99 | invalid date input, token and origin into the URL. | Status error, invalid token, origin message, date appears | { "status": "error", "messages": [ "invalid origin", "invalid date", "invalid token" ] } | Pass
5 | Invalid token, correct origin and blank date , missing k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: | Correct origin, blank date input, invalid token into the URL. | Status error, invalid token, blank date message appears | { "status": "error", "messages": [ "blank date", "invalid token" ] } | Pass
6 | Invalid token, origin and blank date , missing k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: | blank date input, invalid token and origin into the URL. | Status error, invalid token, origin message appears | { "status": "error", "messages": [ "invalid origin", "blank date", "invalid token" ] } | Pass
7 | Invalid token and date, blank origin , missing k | Token: [wrong] Origin Date: 2017-02-06T11:00:99 | invalid date input, token and blank origin into the URL. | Status error, invalid token, origin message, date appears | { "status": "error", "messages": [ "blank origin", "invalid date", "invalid token" ] } | Pass
8 | Invalid token, correct origin, k and date | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: 1 | Correct origin, k and date input, invalid token into the URL. | Status error, invalid token message appears | { "status": "error", "messages": [ "invalid token" ] } | Pass
9 | Invalid token, origin and correct date , k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:01 K: 1 | Correct date input,k , invalid token and origin into the URL. | Status error, invalid token, origin message appears | { "status": "error", "messages": [ "invalid origin", "invalid token" ] } | Pass
10 | Invalid token, origin and date , correct k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:99 K: 1 | invalid date input, token and origin , correct kinto the URL. | Status error, invalid token, origin message, date appears | { "status": "error", "messages": [ "invalid origin", "invalid date", "invalid token" ] } | Pass
11 | Invalid token, correct origin, K and blank date | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: K: 1 | Correct origin, k, blank date input, invalid token into the URL. | Status error, invalid token, blank date message appears | { "status": "error", "messages": [ "blank date", "invalid token" ] } | Pass
12 | Invalid token, origin and blank date , correct k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: K: 1 | correct k, blank date input, invalid token and origin into the URL. | Status error, invalid token, origin message appears | { "status": "error", "messages": [ "invalid origin", "blank date", "invalid token" ] } | Pass
13 | Invalid token and date, blank origin , correct k | Token: [wrong] Origin Date: 2017-02-06T11:00:99 K: 1 | invalid date input, token and origin, correct k into the URL. | Status error, invalid token, origin, date message appears | { "status": "error", "messages": [ "blank origin", "invalid date", "invalid token" ] } | Pass
14 | Correct token, origin and date , blank k | Token: [token value] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: | Correct token, origin and date input, blank k into the URL. | Status error, blank k messageappears | { "status": "error", "messages": [ "blank k" ] } | Pass
15 | Invalid token, correct origin and date, blank k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: | Correct origin and date input, invalid token, blank k into the URL. | Status error, invalid token, blank k message appears | { "status": "error", "messages": [ "blank k", "invalid token" ] } | Pass
16 | Invalid token, origin and correct date , k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:01 K: | Correct date input, blank k , invalid token and origin into the URL. | Status error, invalid token, origin, blank k message appears | { "status": "error", "messages": [ "invalid origin", "blank k", "invalid token" ] } | Pass
17 | Invalid token, origin and date , blank k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: 2017-02-06T11:00:99 K: | invalid date input, token and origin, blank k into the URL. | Status error, invalid token, origin, date , blank k message appears | { "status": "error", "messages": [ "invalid origin", "blank k", "invalid date", "invalid token" ] } | Pass
18 | Invalid token, correct origin and blank date, k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: | Correct origin, date input, blank k, invalid token into the URL. | Status error, invalid token, blank k message appears | { "status": "error", "messages": [ "blank k", "invalid token" ] } | Pass
19 | Invalid token, origin and blank date , k | Token: [wrong] Origin SMUSISL1ReceptionAndLobby123 Date: K: | blank date input, k, invalid token and origin into the URL. | Status error, invalid token, origin, blank date, k message appears | { "status": "error", "messages": [ "invalid origin", "blank k", "blank date", "invalid token" ] } | Pass
20 | Invalid token and date, blank origin , correct k | Token: [wrong] Origin : Date: 2017-02-06T11:00:99 K: | invalid date input, token and blank origin, k into the URL. | Status error, invalid token, origin, date message appears | { "status": "error", "messages": [ "blank origin", "blank k", "invalid date", "invalid token" ] } | Pass
21 | blank token, correct origin and date , missing k | Token: Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 | Blank token, correct origin and date input into the URL. | Status error, blank token message appears | { "status": "error", "messages": [ "blank token" ] } | Pass
22 | blank token, correct origin and date , k | Token: Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: 1 | Blank token, correct origin and date input into the URL. | Status error, blank token message appears | { "status": "error", "messages": [ "blank token" ] } | Pass
23 | invalid origin , correct token, k and date | Token: [token value] Origin SMUSISL1RECEPTIONANDLOBBY Date: 2017-02-06T11:00:00 K: 1 | Blank token, correct origin and date input into the URL. | Status error, invalid token message appears | { "status": "error", "messages": [ "invalid origin" ] } | Pass
24 | Correct token, origin and date , k | Token: [token value] Origin SMUSISL1ReceptionAndLobby Date: 2017-02-06T11:00:00 K: 1 | Correct token, origin, k and date input into the URL. | Status: success, with the different ranks, next places and time together being displayed. | Status success: Output not in order rank { "status": "success", "total-users": 31, "total-next-place-users": 28, "results": [ { "rank": 1, "semantic-place": "SMUSISL1ReceptionAndLobby", "count": 11 }, { "rank": 2, "semantic-place": "SMUSISL2LiftLobby", "count": 3 }, { "rank": 2, "semantic-place": "SMUSISL2StudyArea1", "count": 3 }, { "rank": 3, "semantic-place": "SMUSISL4LiftLobby", "count": 2 }, { "rank": 4, "semantic-place": "SMUSISL3StudyArea3", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL3StudyArea2", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL5StudyArea1", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL4OusideAcadOffice1", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL2SR2.3", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL2StudyArea2", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL4OusideAcadOffice2", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL3LiftLobby", "count": 1 }, { "rank": 4, "semantic-place": "SMUSISL2SR2.2", "count": 1 } ] } | Pass
25
26
27
28
29
30

## Test Case for TopKCompanion
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | User picks: K value, Student macaddress. User Inputs: Correct date Correct time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017 Time: 10:15 AM | User inputs a valid rank, student, date and time and submits form | Queried user is displayed, List of companions to queried user and displays table of companions based on the date and time selected by the user as well as co-location time | Queried user is displayed, List of companions to queried user and displays table of companions based on the date and time selected by the user as well as co-location time | Pass
2 | User picks: K value, Student macaddress. User Inputs: Correct date Correct time | Rank: 3 Student: 0012a371ef9b4472e1ab2397b0db730550c9ec87 Date: 06/02/2017 Time: 10:15 AM | User inputs a valid rank, student, date and time and submits form | Message: No companions found | Message: No companions found | Pass
3 | User picks: K value, Student macaddress. User Inputs: Correct date No time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017 Time: --:-- -- | User inputs a valid rank, student, date and submits form | Form did not allow missing time | Form did not allow missing time | Pass
4 | User picks: K value, Student macaddress. User Inputs: No date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: --/--/---- Time: 10:15 AM | User inputs a valid rank, student, time and submits form | Form did not allow missing date | Form did not allow missing date | Pass
5 | User picks: K value, Student macaddress. User Inputs: No date No time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: --/--/---- Time: --:-- -- | User inputs a valid rank, student, time and submits form | Form did not allow missing datetime | Form did not allow missing datetime | Pass
6 | User picks: K value, Student macaddress. User Inputs: Valid date Invalid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017 Time: aa:15 AM | use inputs time with string | Form did not allow out of range time format | Form did not allow out of range time format | Pass
7 | User picks: K value, Student macaddress. User Inputs: Valid date Invalid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017 Time: 99:15 AM | user inputs invalid hours | Form did not allow out of range time format | Form did not allow out of range time format | Pass
8 | User picks: K value, Student macaddress. User Inputs: Valid date Invalid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/2017 Time: 10:99 AM | user inputs invalid minutes | Form did not allow out of range time format | Form did not allow out of range time format | Pass
9 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: aa/02/2017 Time: 10:15 AM | user inputs day as a string | Form did not allow out of range time format | Form did not allow out of range time format | Pass
10 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/aa/2017 Time: 10:15 AM | user inputs month as a string | Form did not allow out of range time format | Form did not allow out of range time format | Pass
11 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/aaaa Time: 10:15 AM | user inputs year as a string | Form did not allow out of range time format | Form did not allow out of range time format | Pass
12 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 99/02/2017 Time: 10:15 AM | user inputs invalid day | Form did not allow out of range time format | Form did not allow out of range time format | Pass
13 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/99/2017 Time: 10:15 AM | user inputs invalid month | Form did not allow out of range time format | Form did not allow out of range time format | Pass
14 | User picks: K value, Student macaddress. User Inputs: Invalid date Valid time | Rank: 3 Student: 01e4f117e521297e879a35999d990443e067b7b7 Date: 06/02/99999 Time: 10:15 AM | user inputs strange year | Form did not allow year to be past 2025 | Form did not allow year to be past 2025 | Pass

## Test Case for TopKComp JSON
S/N | Description | Inputs | Testing Description | Expected Results | Actual Results | Pass/Fail? | Regression Testing: Pass/Fail?
[6 empty] | Iteration 5 | Iteration 6
1 | Correct token, macAddress, and date , missing k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 | Correct token, macAddress, and date input into the URL. | Status: success, with the different ranks [Default: 3], companion macAddresses and time together being displayed. | { "status": "success", "results": [ { "rank": 1, "companion": "beulah.lam.2016@sis.smu.edu.sg", "mac-address": "787ca8fc7add5df342d9e861997ee8c8b8581dad", "time-together": 887 }, { "rank": 2, "companion": "ettienne.lam.2013@sis.smu.edu.sg", "mac-address": "6a59657c10d6daefc425414e234d9e53d8dc808f", "time-together": 868 }, { "rank": 3, "companion": "enid.lam.2013@sis.smu.edu.sg", "mac-address": "23b700370779c04e5a6dc800ea80f800896d8f75", "time-together": 818 } ] } | Pass
2 | Correct token and macAddrress, wrong time, missing k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 | Correct token, macAddress, and wrong date input into the URL. | Status: error, invalid date | { "status": "error", "messages": [ "invalid date" ] } | Pass
3 | Correct token, wrong macAddress and time ,missing k | Token: [token value] MacAddress: 5945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 | Corect token, wrong macAddress and date input into the URL. | Status: error, invalid time and macAddress | { "status": "error", "messages": [ "invalid mac address", "invalid date" ] } | Pass
4 | Wrong token and macddress, and date , missing k | Token: [wrong] MacAddress: 5945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 | Wrong token, macAddress and date input into the URL. | Status: error, invalid macAddress, time and macAddress | { "status": "error", "messages": [ "invalid mac address", "invalid date", "invalid token" ] } | Pass
5 | Correct token and macAddress, missing date and k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc | Correct token, macAddress and missing date input into the URL. | Status: error, missing date | { "status": "error", "messages": [ "missing date" ] } | (FAIL during AWS testing, bug has been fixed, tested and passed in local after bug fix)Pass
6 | Correct token, missing macAddress, k and date | Token: [token value] | Correct token, macAddress and missing date input into the URL. | Status: error, missing macAddress and date | { "status": "error", "messages": [ "missing macAddress", "missing date" ] } | (FAIL during AWS testing, bug has been fixed, tested and passed in local after bug fix)Pass
7 | Missing token,k and macAddress and date | - | Missing token, macAddress, date input in the URL. | Status: error, missing macAddress and date | { "status": "error", "messages": [ "missing macAddress", "missing date", "missing token" ] } | (FAIL during AWS testing, bug has been fixed, tested and passed in local after bug fix)Pass
8 | Correct token, correct macAddress , missing k and blank date | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: | Correct token, macAddress, blank date input in the URL. | Status: error, blank date | { "status": "error", "messages": [ "blank date" ] } | Pass
8 | Correct token, , missing k, blank macAddres and blank date | Token: [token value] MacAddress: Date: | Correct token, blank macAddress and date input in the URL. | Status: error, blank macAddress and date | { "status": "error", "messages": [ "blank mac address", "blank date" ] } | Pass
9 | Blank token, macAddress and date , missing k | Token: MacAddress: Date: | Blank token, macAddress and date input in the URL. | Status: error, blank token, macAddress and date | { "status": "error", "messages": [ "blank mac address", "blank date", "blank token" ] } | Pass
10 | Correct token, macAddress, and date , blank k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: | Correct token, macAddress, and date input and blank k into the URL. | Status: error, blank k | { "status": "error", "messages": [ "blank k" ] } | Pass
11 | Correct token and macAddrress, wrong time, blank k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 K: | Correct token, macAddress, blank k and wrong date input into the URL. | Status: error, invalid date, blank k | { "status": "error", "messages": [ "blank k", "invalid date" ] } | Pass
12 | Correct token, wrong macAddress and time, blank k | Token: [token value] MacAddress: 5945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 K: | Corect token, wrong macAddress and date input, blank k into the URL. | Status: error, invalid time and macAddress, blank k | { "status": "error", "messages": [ "blank k", "invalid mac address", "invalid date" ] } | Pass
13 | Wrong token and macddress, and date , blank k | Token: [wrong] MacAddress: 5945cbc65122c753a9ee3df2755ac0bc Date: 2017T11:15:00 K: | Wrong token, macAddress and date input, blank k into the URL. | Status: error, invalid macAddress, time and macAddress, blank k | { "status": "error", "messages": [ "blank k", "invalid mac address", "invalid date", "invalid token" ] } | Pass
14 | Correct token and macAddress, missing date and blank k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc K: | Correct token, macAddress, blank k and missing date input into the URL. | Status: error, missing date, blank k | { "status": "error", "messages": [ "blank k", "missing date" ] } | Pass
15 | Correct token, missing macAddress and date , blank k | Token: [token value] K: | Correct token, blank k, macAddress and missing date input into the URL. | Status: error, missing macAddress and date, blank k | { "status": "error", "messages": [ "blank k", "missing macAddress", "missing date" ] } | Pass
16 | Missing token , macAddress and date , blank k | K: | Missing token, macAddress, date input, blank k in the URL. | Status: error, missing macAddress and date, blank k | { "status": "error", "messages": [ "blank k", "missing macAddress", "missing date", "missing token" ] } | Pass
17 | Correct token, correct macAddress and blank date, k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: K: | Correct token, macAddress, blank date, kinput in the URL. | Status: error, blank date, blank k | { "status": "error", "messages": [ "blank k", "blank date" ] } | Pass
18 | Correct token, blank k, blank macAddres and blank date | Token: [token value] MacAddress: Date: | Correct token, blank macAddress, k and date input in the URL. | Status: error, blank macAddress, k and date | { "status": "error", "messages": [ "blank k", "blank mac address", "blank date" ] } | Pass
19 | Blank token, macAddress, date and k | Token: MacAddress: Date: K: | Blank token, K , macAddress and date input in the URL. | Status: error, blank token, k , macAddress and date | { "status": "error", "messages": [ "blank k", "blank mac address", "blank date", "blank token" ] } | Pass
20 | Correct token, macAddress, and date , invalid k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: "abc" | Correct token, macAddress, and date input, invalid k into the URL. | Status:error, invalid k | { "status": "error", "messages": [ "invalid k" ] } | Pass
21 | Correct token, macAddress, and date , invalid k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: "-2" | Correct token, macAddress, and date input, invalid k into the URL. | Status:error, invalid k | { "status": "error", "messages": [ "invalid k" ] } | Pass
22 | Correct token, macAddress, and date , invalid k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: "12" | Correct token, macAddress, and date input, invalid k into the URL. | Status:error, invalid k | { "status": "error", "messages": [ "invalid k" ] } | Pass
23 | Correct token, macAddress, and date , invalid k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: "5.5" | Correct token, macAddress, and date input, invalid k into the URL. | Status:error, invalid k | { "status": "error", "messages": [ "invalid k" ] } | Pass
24 | Correct token, macAddress, and date , invalid k | Token: [token value] MacAddress: 02e66bb05945cbc65122c753a9ee3df2755ac0bc Date: 2017-02-06T11:00:00 K: "0" | Correct token, macAddress, and date input, invalid k into the URL. | Status:error, invalid k | { "status": "error", "messages": [ "invalid k" ] } | Pass
25
26
27
28
29
30
31