## Bug Metrics
IS203 G1-T3 Bug Metrics | [6 empty] | Points Calculation: Total = 1 x num (low) + 5 x num (high) + 10 x num (critical)
Iteration | Number of Bugs | Number of Low Impact | Number of High Impact | Number of Critical Impact | Bug Metrics Points | Action Done
2 | 5 | 0 | 5 | 0 | 25 | Insert debugging sessions to resolve the bugs
3 | 2 | 1 | 1 | 0 | 6 | Insert debugging session after deployment to resolve the bugs
4 | 6 | 2 | 4 | 0 | 22 | Insert debugging session after deployment to resolve the bugs
5 | 15 | 4 | 11 | 0 | 59 | An emergency debugging session was added to update the code according to the change in wiki requirements before UAT. Debugging sessions were added to resolve bugs identified after manual and automated UAT.
6 | 0 | 0 | 2 | 0 | 10 | Bugs were identified during UAT and resolved in debugging sessions before the final deployment.
7
Total | 28 | 7 | 23 | 0 | 122

## Bug Log
Iteration | Task S/N | Description | Where did it occur | How to reproduce | Who found it | Date Found | Date Solved | Time Taken (hr) | Severity (Impact) | Points Allocation | Point Accumulated Per Iteration | Status | Action | Pair Programmers